## Tasks
Sprint Number | Assignee | Team | Task Title | Task Description | Task start date | Task end date | Status | Priority | Story Point
1 | BE_Sophia | Backend | Authentication/Session: Crafting & Upgrades | Backend task for 'Crafting & Upgrades'. Deliverable sized to 3 SP. | 2025-01-07 | 2025-01-08 | Done | High | 3
1 | BE_Sophia | Backend | Performance tuning: Offline Mode | Backend task for 'Offline Mode'. Deliverable sized to 3 SP. | 2025-01-09 | 2025-01-11 | Done | High | 3
1 | BE_Michael | Backend | Leaderboard/Guild service: Level Generator | Backend task for 'Level Generator'. Deliverable sized to 5 SP. | 2025-01-12 | 2025-01-15 | Done | Medium | 5
1 | BE_Sophia | Backend | API endpoint: Accessibility | Backend task for 'Accessibility'. Deliverable sized to 3 SP. | 2025-01-09 | 2025-01-10 | Done | High | 3
1 | BE_Ava | Backend | Leaderboard/Guild service: Anti-cheat | Backend task for 'Anti-cheat'. Deliverable sized to 8 SP. | 2025-01-12 | 2025-01-16 | Done | Low | 8
1 | BE_Michael | Backend | Game logic service: Weekly Boss Chase | Backend task for 'Weekly Boss Chase'. Deliverable sized to 5 SP. | 2025-01-09 | 2025-01-12 | Done | Medium | 5
1 | BA_Alice | Business Analyst | User stories: Weekly Boss Chase | Business Analyst task for 'Weekly Boss Chase'. Deliverable sized to 5 SP. | 2025-01-09 | 2025-01-10 | Done | Medium | 5
1 | BA_Alice | Business Analyst | Backlog refinement: Live Ops Tooling | Business Analyst task for 'Live Ops Tooling'. Deliverable sized to 3 SP. | 2025-01-07 | 2025-01-09 | Done | Low | 3
1 | BA_John | Business Analyst | Backlog refinement: Daily Challenges | Business Analyst task for 'Daily Challenges'. Deliverable sized to 8 SP. | 2025-01-06 | 2025-01-09 | Done | Medium | 8
1 | Data_Liam | Data Team | ETL pipeline: Character Customization | Data Team task for 'Character Customization'. Deliverable sized to 3 SP. | 2025-01-16 | 2025-01-18 | Done | Medium | 3
1 | Data_Liam | Data Team | Balance analysis: Crafting & Upgrades | Data Team task for 'Crafting & Upgrades'. Deliverable sized to 3 SP. | 2025-01-15 | 2025-01-17 | Done | Medium | 3
1 | Data_Liam | Data Team | Balance analysis: Social Sharing | Data Team task for 'Social Sharing'. Deliverable sized to 3 SP. | 2025-01-07 | 2025-01-08 | Done | High | 3
1 | FE_David | Frontend | Responsive layout: Live Ops Tooling | Frontend task for 'Live Ops Tooling'. Deliverable sized to 3 SP. | 2025-01-16 | 2025-01-17 | Done | Medium | 3
1 | FE_Emily | Frontend | UX polish: Live Ops Tooling | Frontend task for 'Live Ops Tooling'. Deliverable sized to 5 SP. | 2025-01-10 | 2025-01-11 | Done | High | 5
1 | FE_Noah | Frontend | UX polish: Localization | Frontend task for 'Localization'. Deliverable sized to 8 SP. | 2025-01-08 | 2025-01-13 | Done | Medium | 8
1 | FE_David | Frontend | Responsive layout: Guilds & Chat | Frontend task for 'Guilds & Chat'. Deliverable sized to 5 SP. | 2025-01-08 | 2025-01-10 | Done | Medium | 5
1 | FE_Emily | Frontend | UI integration test fixes: Inventory | Frontend task for 'Inventory'. Deliverable sized to 5 SP. | 2025-01-09 | 2025-01-12 | Done | Low | 5
1 | QA_Olivia | QA | Test plan: Shop & IAP | QA task for 'Shop & IAP'. Deliverable sized to 3 SP. | 2025-01-07 | 2025-01-09 | Done | Low | 3
1 | QA_Olivia | QA | Test data setup: Inventory | QA task for 'Inventory'. Deliverable sized to 3 SP. | 2025-01-10 | 2025-01-11 | Done | Medium | 3
1 | QA_Daniel | QA | Exploratory testing: Pet Companions | QA task for 'Pet Companions'. Deliverable sized to 3 SP. | 2025-01-11 | 2025-01-13 | Done | Low | 3
1 | QA_Olivia | QA | Test plan: Analytics & Telemetry | QA task for 'Analytics & Telemetry'. Deliverable sized to 3 SP. | 2025-01-12 | 2025-01-13 | Done | Medium | 3
1 | QA_Daniel | QA | Test data setup: Guilds & Chat | QA task for 'Guilds & Chat'. Deliverable sized to 5 SP. | 2025-01-10 | 2025-01-11 | Done | High | 5
2 | BE_Sophia | Backend | Leaderboard/Guild service: Weekly Boss Chase | Backend task for 'Weekly Boss Chase'. Deliverable sized to 3 SP. | 2025-01-23 | 2025-01-24 | Done | Medium | 3
2 | BE_Michael | Backend | Leaderboard/Guild service: Live Ops Tooling | Backend task for 'Live Ops Tooling'. Deliverable sized to 3 SP. | 2025-01-25 | 2025-01-27 | Done | Medium | 3
2 | BE_Sophia | Backend | API endpoint: Obstacle Library | Backend task for 'Obstacle Library'. Deliverable sized to 5 SP. | 2025-01-25 | 2025-01-26 | Done | Medium | 5
2 | BE_Ava | Backend | API endpoint: Beta Release | Backend task for 'Beta Release'. Deliverable sized to 3 SP. | 2025-01-23 | 2025-01-24 | Done | Low | 3
2 | BE_Ava | Backend | API endpoint: Offline Mode | Backend task for 'Offline Mode'. Deliverable sized to 5 SP. | 2025-01-20 | 2025-01-22 | Done | Medium | 5
2 | BE_Michael | Backend | Leaderboard/Guild service: Daily Challenges | Backend task for 'Daily Challenges'. Deliverable sized to 5 SP. | 2025-01-26 | 2025-01-27 | Done | Low | 5
2 | BA_Alice | Business Analyst | Acceptance criteria: Onboarding & Tutorial | Business Analyst task for 'Onboarding & Tutorial'. Deliverable sized to 3 SP. | 2025-01-28 | 2025-01-29 | Done | Medium | 3
2 | BA_Alice | Business Analyst | Epic scoping: Onboarding & Tutorial | Business Analyst task for 'Onboarding & Tutorial'. Deliverable sized to 3 SP. | 2025-01-30 | 2025-02-01 | Done | High | 3
2 | BA_Alice | Business Analyst | Epic scoping: Shop & IAP | Business Analyst task for 'Shop & IAP'. Deliverable sized to 3 SP. | 2025-01-24 | 2025-01-26 | Done | Low | 3
2 | BA_John | Business Analyst | Acceptance criteria: Offline Mode | Business Analyst task for 'Offline Mode'. Deliverable sized to 8 SP. | 2025-01-23 | 2025-01-26 | Done | Medium | 8
2 | Data_Liam | Data Team | Event schema: Analytics & Telemetry | Data Team task for 'Analytics & Telemetry'. Deliverable sized to 3 SP. | 2025-01-20 | 2025-01-21 | Done | High | 3
2 | Data_Liam | Data Team | Balance analysis: Weekly Boss Chase | Data Team task for 'Weekly Boss Chase'. Deliverable sized to 5 SP. | 2025-01-23 | 2025-01-24 | Done | Medium | 5
2 | FE_David | Frontend | Responsive layout: Live Ops Tooling | Frontend task for 'Live Ops Tooling'. Deliverable sized to 3 SP. | 2025-01-27 | 2025-01-29 | Done | Low | 3
2 | FE_David | Frontend | UI integration test fixes: Level Generator | Frontend task for 'Level Generator'. Deliverable sized to 5 SP. | 2025-01-23 | 2025-01-26 | Done | Medium | 5
2 | FE_Emily | Frontend | Animations & VFX: Character Customization | Frontend task for 'Character Customization'. Deliverable sized to 3 SP. | 2025-01-28 | 2025-01-29 | Done | Medium | 3
2 | FE_Emily | Frontend | Animations & VFX: Localization | Frontend task for 'Localization'. Deliverable sized to 5 SP. | 2025-01-21 | 2025-01-24 | Done | High | 5
2 | FE_Noah | Frontend | Implement UI: Shop & IAP | Frontend task for 'Shop & IAP'. Deliverable sized to 8 SP. | 2025-01-23 | 2025-01-26 | Done | Low | 8
2 | QA_Daniel | QA | Test data setup: Accessibility | QA task for 'Accessibility'. Deliverable sized to 8 SP. | 2025-01-20 | 2025-01-24 | Done | Medium | 8
2 | QA_Olivia | QA | Regression suite update: Inventory | QA task for 'Inventory'. Deliverable sized to 8 SP. | 2025-01-23 | 2025-01-25 | Done | Low | 8
3 | BE_Michael | Backend | Authentication/Session: Analytics & Telemetry | Backend task for 'Analytics & Telemetry'. Deliverable sized to 3 SP. | 2025-02-13 | 2025-02-14 | Done | High | 3
3 | BE_Michael | Backend | Performance tuning: Season Pass | Backend task for 'Season Pass'. Deliverable sized to 5 SP. | 2025-02-11 | 2025-02-12 | Done | Medium | 5
3 | BE_Sophia | Backend | API endpoint: Inventory | Backend task for 'Inventory'. Deliverable sized to 8 SP. | 2025-02-06 | 2025-02-10 | Done | Medium | 8
3 | BE_Ava | Backend | API endpoint: Power-ups & Boosts | Backend task for 'Power-ups & Boosts'. Deliverable sized to 8 SP. | 2025-02-05 | 2025-02-09 | Done | Medium | 8
3 | BA_Alice | Business Analyst | Epic scoping: Crafting & Upgrades | Business Analyst task for 'Crafting & Upgrades'. Deliverable sized to 5 SP. | 2025-02-05 | 2025-02-07 | Done | Low | 5
3 | BA_Alice | Business Analyst | Stakeholder workshop: Pet Companions | Business Analyst task for 'Pet Companions'. Deliverable sized to 5 SP. | 2025-02-10 | 2025-02-12 | Done | Low | 5
3 | BA_John | Business Analyst | Backlog refinement: Localization | Business Analyst task for 'Localization'. Deliverable sized to 5 SP. | 2025-02-10 | 2025-02-11 | Done | Low | 5
3 | BA_John | Business Analyst | Stakeholder workshop: Beta Release | Business Analyst task for 'Beta Release'. Deliverable sized to 5 SP. | 2025-02-07 | 2025-02-09 | Done | Medium | 5
3 | Data_Liam | Data Team | ETL pipeline: Shop & IAP | Data Team task for 'Shop & IAP'. Deliverable sized to 8 SP. | 2025-02-07 | 2025-02-12 | Done | Medium | 8
3 | FE_Emily | Frontend | UI integration test fixes: Power-ups & Boosts | Frontend task for 'Power-ups & Boosts'. Deliverable sized to 8 SP. | 2025-02-06 | 2025-02-08 | Done | Medium | 8
3 | FE_David | Frontend | Responsive layout: Social Sharing | Frontend task for 'Social Sharing'. Deliverable sized to 5 SP. | 2025-02-07 | 2025-02-08 | Done | Medium | 5
3 | FE_Noah | Frontend | Implement UI: Anti-cheat | Frontend task for 'Anti-cheat'. Deliverable sized to 3 SP. | 2025-02-04 | 2025-02-05 | Done | Medium | 3
3 | FE_David | Frontend | UX polish: Shop & IAP | Frontend task for 'Shop & IAP'. Deliverable sized to 3 SP. | 2025-02-07 | 2025-02-09 | Done | Low | 3
3 | FE_Noah | Frontend | Implement UI: Accessibility | Frontend task for 'Accessibility'. Deliverable sized to 5 SP. | 2025-02-03 | 2025-02-05 | Done | Medium | 5
3 | QA_Daniel | QA | Test data setup: Core Runner Mechanics | QA task for 'Core Runner Mechanics'. Deliverable sized to 8 SP. | 2025-02-03 | 2025-02-07 | Done | Low | 8
3 | QA_Olivia | QA | Functional test: Social Sharing | QA task for 'Social Sharing'. Deliverable sized to 5 SP. | 2025-02-03 | 2025-02-06 | Done | Low | 5
3 | QA_Olivia | QA | Test plan: Pet Companions | QA task for 'Pet Companions'. Deliverable sized to 3 SP. | 2025-02-12 | 2025-02-13 | Done | Medium | 3
4 | BE_Michael | Backend | Leaderboard/Guild service: Shop & IAP | Backend task for 'Shop & IAP'. Deliverable sized to 5 SP. | 2025-02-25 | 2025-02-26 | Done | Medium | 5
4 | BE_Sophia | Backend | Game logic service: Weekly Boss Chase | Backend task for 'Weekly Boss Chase'. Deliverable sized to 8 SP. | 2025-02-21 | 2025-02-23 | Done | Low | 8
4 | BE_Ava | Backend | Performance tuning: Beta Release | Backend task for 'Beta Release'. Deliverable sized to 8 SP. | 2025-02-20 | 2025-02-24 | Done | Medium | 8
4 | BE_Michael | Backend | Game logic service: Anti-cheat | Backend task for 'Anti-cheat'. Deliverable sized to 5 SP. | 2025-02-21 | 2025-02-22 | Done | Medium | 5
4 | BA_Alice | Business Analyst | User stories: Accessibility | Business Analyst task for 'Accessibility'. Deliverable sized to 3 SP. | 2025-02-27 | 2025-03-01 | Done | Low | 3
4 | BA_John | Business Analyst | User stories: A/B Testing Framework | Business Analyst task for 'A/B Testing Framework'. Deliverable sized to 5 SP. | 2025-02-25 | 2025-02-26 | Done | High | 5
4 | BA_Alice | Business Analyst | Stakeholder workshop: Offline Mode | Business Analyst task for 'Offline Mode'. Deliverable sized to 5 SP. | 2025-02-21 | 2025-02-22 | Done | Low | 5
4 | BA_John | Business Analyst | Epic scoping: Analytics & Telemetry | Business Analyst task for 'Analytics & Telemetry'. Deliverable sized to 5 SP. | 2025-02-18 | 2025-02-19 | Done | High | 5
4 | Data_Liam | Data Team | A/B experiment design: Shop & IAP | Data Team task for 'Shop & IAP'. Deliverable sized to 3 SP. | 2025-02-22 | 2025-02-23 | Done | Medium | 3
4 | Data_Liam | Data Team | Dashboard build: A/B Testing Framework | Data Team task for 'A/B Testing Framework'. Deliverable sized to 3 SP. | 2025-02-25 | 2025-02-26 | Done | Low | 3
4 | Data_Liam | Data Team | A/B experiment design: Season Pass | Data Team task for 'Season Pass'. Deliverable sized to 3 SP. | 2025-02-21 | 2025-02-23 | Done | Medium | 3
4 | FE_Emily | Frontend | UX polish: Leaderboard | Frontend task for 'Leaderboard'. Deliverable sized to 5 SP. | 2025-02-21 | 2025-02-22 | Done | High | 5
4 | FE_David | Frontend | Responsive layout: Crafting & Upgrades | Frontend task for 'Crafting & Upgrades'. Deliverable sized to 3 SP. | 2025-02-21 | 2025-02-22 | Done | High | 3
4 | FE_Emily | Frontend | Animations & VFX: Power-ups & Boosts | Frontend task for 'Power-ups & Boosts'. Deliverable sized to 5 SP. | 2025-02-17 | 2025-02-19 | Done | Low | 5
4 | FE_Noah | Frontend | UI integration test fixes: Offline Mode | Frontend task for 'Offline Mode'. Deliverable sized to 8 SP. | 2025-02-23 | 2025-02-27 | Done | High | 8
4 | FE_David | Frontend | UX polish: Season Pass | Frontend task for 'Season Pass'. Deliverable sized to 5 SP. | 2025-02-20 | 2025-02-21 | Done | Medium | 5
4 | QA_Daniel | QA | Test plan: Character Customization | QA task for 'Character Customization'. Deliverable sized to 5 SP. | 2025-02-21 | 2025-02-23 | Done | High | 5
4 | QA_Daniel | QA | Test plan: Beta Release | QA task for 'Beta Release'. Deliverable sized to 3 SP. | 2025-02-22 | 2025-02-23 | Done | Medium | 3
4 | QA_Olivia | QA | Functional test: Beta Release | QA task for 'Beta Release'. Deliverable sized to 3 SP. | 2025-02-23 | 2025-02-24 | Done | Low | 3
4 | QA_Olivia | QA | Exploratory testing: Analytics & Telemetry | QA task for 'Analytics & Telemetry'. Deliverable sized to 5 SP. | 2025-02-19 | 2025-02-20 | Done | High | 5
5 | BE_Michael | Backend | Game logic service: Season Pass | Backend task for 'Season Pass'. Deliverable sized to 8 SP. | 2025-03-07 | 2025-03-11 | Done | Medium | 8
5 | BE_Ava | Backend | Leaderboard/Guild service: Leaderboard | Backend task for 'Leaderboard'. Deliverable sized to 3 SP. | 2025-03-08 | 2025-03-10 | Done | Medium | 3
5 | BE_Ava | Backend | Leaderboard/Guild service: Daily Challenges | Backend task for 'Daily Challenges'. Deliverable sized to 5 SP. | 2025-03-05 | 2025-03-08 | Done | Low | 5
5 | BE_Sophia | Backend | Performance tuning: Accessibility | Backend task for 'Accessibility'. Deliverable sized to 8 SP. | 2025-03-10 | 2025-03-13 | Done | Medium | 8
5 | BA_Alice | Business Analyst | Acceptance criteria: Onboarding & Tutorial | Business Analyst task for 'Onboarding & Tutorial'. Deliverable sized to 3 SP. | 2025-03-07 | 2025-03-08 | Done | Medium | 3
5 | BA_John | Business Analyst | User stories: Push Notifications | Business Analyst task for 'Push Notifications'. Deliverable sized to 5 SP. | 2025-03-04 | 2025-03-06 | Done | Medium | 5
5 | BA_Alice | Business Analyst | User stories: Localization | Business Analyst task for 'Localization'. Deliverable sized to 5 SP. | 2025-03-07 | 2025-03-09 | Done | Medium | 5
5 | BA_John | Business Analyst | Stakeholder workshop: Guilds & Chat | Business Analyst task for 'Guilds & Chat'. Deliverable sized to 5 SP. | 2025-03-10 | 2025-03-13 | Done | Low | 5
5 | Data_Liam | Data Team | Balance analysis: Leaderboard | Data Team task for 'Leaderboard'. Deliverable sized to 8 SP. | 2025-03-03 | 2025-03-08 | Done | Medium | 8
5 | FE_Noah | Frontend | Animations & VFX: Push Notifications | Frontend task for 'Push Notifications'. Deliverable sized to 3 SP. | 2025-03-07 | 2025-03-08 | Done | High | 3
5 | FE_Noah | Frontend | UI integration test fixes: Launch & Post-Launch | Frontend task for 'Launch & Post-Launch'. Deliverable sized to 5 SP. | 2025-03-10 | 2025-03-11 | Done | Medium | 5
5 | FE_David | Frontend | UI integration test fixes: Analytics & Telemetry | Frontend task for 'Analytics & Telemetry'. Deliverable sized to 3 SP. | 2025-03-08 | 2025-03-10 | Done | Medium | 3
5 | FE_David | Frontend | Animations & VFX: Power-ups & Boosts | Frontend task for 'Power-ups & Boosts'. Deliverable sized to 3 SP. | 2025-03-05 | 2025-03-07 | Done | Medium | 3
5 | FE_Emily | Frontend | Implement UI: Accessibility | Frontend task for 'Accessibility'. Deliverable sized to 8 SP. | 2025-03-09 | 2025-03-12 | Done | Low | 8
5 | FE_David | Frontend | Animations & VFX: Social Sharing | Frontend task for 'Social Sharing'. Deliverable sized to 3 SP. | 2025-03-03 | 2025-03-04 | Done | High | 3
5 | QA_Olivia | QA | Exploratory testing: Push Notifications | QA task for 'Push Notifications'. Deliverable sized to 5 SP. | 2025-03-06 | 2025-03-07 | Done | Medium | 5
5 | QA_Daniel | QA | Functional test: Launch & Post-Launch | QA task for 'Launch & Post-Launch'. Deliverable sized to 5 SP. | 2025-03-07 | 2025-03-08 | Done | High | 5
5 | QA_Olivia | QA | Exploratory testing: Guilds & Chat | QA task for 'Guilds & Chat'. Deliverable sized to 5 SP. | 2025-03-06 | 2025-03-09 | Done | Medium | 5
5 | QA_Daniel | QA | Test plan: Character Customization | QA task for 'Character Customization'. Deliverable sized to 3 SP. | 2025-03-03 | 2025-03-04 | Done | High | 3
6 | BE_Ava | Backend | Performance tuning: Pet Companions | Backend task for 'Pet Companions'. Deliverable sized to 3 SP. | 2025-03-27 | 2025-03-29 | Done | Medium | 3
6 | BE_Michael | Backend | API endpoint: Inventory | Backend task for 'Inventory'. Deliverable sized to 3 SP. | 2025-03-25 | 2025-03-27 | Done | Low | 3
6 | BE_Sophia | Backend | Game logic service: Anti-cheat | Backend task for 'Anti-cheat'. Deliverable sized to 8 SP. | 2025-03-18 | 2025-03-22 | Done | High | 8
6 | BE_Michael | Backend | API endpoint: Anti-cheat | Backend task for 'Anti-cheat'. Deliverable sized to 5 SP. | 2025-03-22 | 2025-03-25 | Done | Medium | 5
6 | BE_Ava | Backend | Authentication/Session: Leaderboard | Backend task for 'Leaderboard'. Deliverable sized to 5 SP. | 2025-03-24 | 2025-03-27 | Done | Low | 5
6 | BA_John | Business Analyst | User stories: Leaderboard | Business Analyst task for 'Leaderboard'. Deliverable sized to 3 SP. | 2025-03-24 | 2025-03-25 | Done | Low | 3
6 | BA_John | Business Analyst | Acceptance criteria: Crafting & Upgrades | Business Analyst task for 'Crafting & Upgrades'. Deliverable sized to 3 SP. | 2025-03-20 | 2025-03-22 | Done | Medium | 3
6 | BA_John | Business Analyst | Epic scoping: Analytics & Telemetry | Business Analyst task for 'Analytics & Telemetry'. Deliverable sized to 3 SP. | 2025-03-23 | 2025-03-24 | Done | Low | 3
6 | BA_Alice | Business Analyst | Stakeholder workshop: Season Pass | Business Analyst task for 'Season Pass'. Deliverable sized to 3 SP. | 2025-03-23 | 2025-03-24 | Done | Medium | 3
6 | BA_Alice | Business Analyst | Stakeholder workshop: Live Ops Tooling | Business Analyst task for 'Live Ops Tooling'. Deliverable sized to 3 SP. | 2025-03-19 | 2025-03-21 | Done | High | 3
6 | BA_Alice | Business Analyst | Stakeholder workshop: Weekly Boss Chase | Business Analyst task for 'Weekly Boss Chase'. Deliverable sized to 3 SP. | 2025-03-24 | 2025-03-25 | Done | Medium | 3
6 | Data_Liam | Data Team | Balance analysis: Guilds & Chat | Data Team task for 'Guilds & Chat'. Deliverable sized to 5 SP. | 2025-03-21 | 2025-03-23 | Done | High | 5
6 | Data_Liam | Data Team | Event schema: Launch & Post-Launch | Data Team task for 'Launch & Post-Launch'. Deliverable sized to 5 SP. | 2025-03-21 | 2025-03-23 | Done | Low | 5
6 | FE_David | Frontend | Responsive layout: A/B Testing Framework | Frontend task for 'A/B Testing Framework'. Deliverable sized to 5 SP. | 2025-03-22 | 2025-03-23 | Done | Medium | 5
6 | FE_David | Frontend | Implement UI: Localization | Frontend task for 'Localization'. Deliverable sized to 3 SP. | 2025-03-19 | 2025-03-21 | Done | Low | 3
6 | FE_Noah | Frontend | UI integration test fixes: Season Pass | Frontend task for 'Season Pass'. Deliverable sized to 8 SP. | 2025-03-23 | 2025-03-28 | Done | High | 8
6 | FE_Emily | Frontend | UX polish: Character Customization | Frontend task for 'Character Customization'. Deliverable sized to 8 SP. | 2025-03-19 | 2025-03-24 | Done | Medium | 8
6 | QA_Daniel | QA | Test data setup: Localization | QA task for 'Localization'. Deliverable sized to 3 SP. | 2025-03-17 | 2025-03-19 | Done | Low | 3
6 | QA_Olivia | QA | Test plan: Offline Mode | QA task for 'Offline Mode'. Deliverable sized to 8 SP. | 2025-03-17 | 2025-03-20 | Done | Low | 8
6 | QA_Daniel | QA | Exploratory testing: Accessibility | QA task for 'Accessibility'. Deliverable sized to 5 SP. | 2025-03-21 | 2025-03-22 | Done | Medium | 5
7 | BE_Michael | Backend | Game logic service: Character Customization | Backend task for 'Character Customization'. Deliverable sized to 5 SP. | 2025-04-04 | 2025-04-05 | Done | High | 5
7 | BE_Ava | Backend | Leaderboard/Guild service: Crafting & Upgrades | Backend task for 'Crafting & Upgrades'. Deliverable sized to 5 SP. | 2025-04-07 | 2025-04-09 | Done | High | 5
7 | BE_Sophia | Backend | API endpoint: Push Notifications | Backend task for 'Push Notifications'. Deliverable sized to 8 SP. | 2025-04-01 | 2025-04-06 | Done | Medium | 8
7 | BE_Michael | Backend | Performance tuning: Power-ups & Boosts | Backend task for 'Power-ups & Boosts'. Deliverable sized to 5 SP. | 2025-04-06 | 2025-04-09 | Done | Medium | 5
7 | BE_Ava | Backend | Authentication/Session: Leaderboard | Backend task for 'Leaderboard'. Deliverable sized to 5 SP. | 2025-03-31 | 2025-04-03 | Done | High | 5
7 | BA_John | Business Analyst | Epic scoping: Level Generator | Business Analyst task for 'Level Generator'. Deliverable sized to 5 SP. | 2025-04-03 | 2025-04-06 | Done | Medium | 5
7 | BA_Alice | Business Analyst | Acceptance criteria: Crafting & Upgrades | Business Analyst task for 'Crafting & Upgrades'. Deliverable sized to 5 SP. | 2025-03-31 | 2025-04-02 | Done | High | 5
7 | BA_John | Business Analyst | Acceptance criteria: A/B Testing Framework | Business Analyst task for 'A/B Testing Framework'. Deliverable sized to 5 SP. | 2025-04-08 | 2025-04-09 | Done | Medium | 5
7 | BA_Alice | Business Analyst | Stakeholder workshop: Pet Companions | Business Analyst task for 'Pet Companions'. Deliverable sized to 5 SP. | 2025-04-03 | 2025-04-05 | Done | High | 5
7 | Data_Liam | Data Team | ETL pipeline: Accessibility | Data Team task for 'Accessibility'. Deliverable sized to 8 SP. | 2025-04-03 | 2025-04-07 | Done | Medium | 8
7 | FE_Emily | Frontend | UI integration test fixes: Localization | Frontend task for 'Localization'. Deliverable sized to 5 SP. | 2025-04-02 | 2025-04-03 | Done | Low | 5
7 | FE_David | Frontend | Responsive layout: Character Customization | Frontend task for 'Character Customization'. Deliverable sized to 3 SP. | 2025-03-31 | 2025-04-01 | Done | Medium | 3
7 | FE_David | Frontend | UX polish: Inventory | Frontend task for 'Inventory'. Deliverable sized to 5 SP. | 2025-04-04 | 2025-04-05 | Done | Medium | 5
7 | FE_Noah | Frontend | Animations & VFX: Push Notifications | Frontend task for 'Push Notifications'. Deliverable sized to 3 SP. | 2025-04-07 | 2025-04-09 | Done | Low | 3
7 | FE_Noah | Frontend | Animations & VFX: Accessibility | Frontend task for 'Accessibility'. Deliverable sized to 5 SP. | 2025-04-01 | 2025-04-02 | Done | Medium | 5
7 | FE_Emily | Frontend | Responsive layout: Push Notifications | Frontend task for 'Push Notifications'. Deliverable sized to 3 SP. | 2025-04-09 | 2025-04-11 | Done | High | 3
7 | QA_Daniel | QA | Exploratory testing: Push Notifications | QA task for 'Push Notifications'. Deliverable sized to 5 SP. | 2025-04-07 | 2025-04-08 | Done | Low | 5
7 | QA_Olivia | QA | Regression suite update: Guilds & Chat | QA task for 'Guilds & Chat'. Deliverable sized to 3 SP. | 2025-04-04 | 2025-04-06 | Done | Low | 3
7 | QA_Daniel | QA | Exploratory testing: Daily Challenges | QA task for 'Daily Challenges'. Deliverable sized to 3 SP. | 2025-04-03 | 2025-04-05 | Done | Medium | 3
7 | QA_Olivia | QA | Exploratory testing: Inventory | QA task for 'Inventory'. Deliverable sized to 5 SP. | 2025-04-08 | 2025-04-10 | Done | Medium | 5
8 | BE_Sophia | Backend | Authentication/Session: Pet Companions | Backend task for 'Pet Companions'. Deliverable sized to 5 SP. | 2025-04-20 | 2025-04-23 | Done | Medium | 5
8 | BE_Ava | Backend | Performance tuning: Level Generator | Backend task for 'Level Generator'. Deliverable sized to 5 SP. | 2025-04-19 | 2025-04-22 | Done | High | 5
8 | BE_Michael | Backend | API endpoint: Shop & IAP | Backend task for 'Shop & IAP'. Deliverable sized to 8 SP. | 2025-04-20 | 2025-04-22 | Done | Medium | 8
8 | BE_Ava | Backend | Leaderboard/Guild service: Offline Mode | Backend task for 'Offline Mode'. Deliverable sized to 3 SP. | 2025-04-14 | 2025-04-15 | Done | Medium | 3
8 | BE_Sophia | Backend | Leaderboard/Guild service: Live Ops Tooling | Backend task for 'Live Ops Tooling'. Deliverable sized to 5 SP. | 2025-04-22 | 2025-04-23 | Done | Medium | 5
8 | BA_John | Business Analyst | Epic scoping: Season Pass | Business Analyst task for 'Season Pass'. Deliverable sized to 5 SP. | 2025-04-17 | 2025-04-19 | Done | Medium | 5
8 | BA_Alice | Business Analyst | Backlog refinement: Pet Companions | Business Analyst task for 'Pet Companions'. Deliverable sized to 8 SP. | 2025-04-15 | 2025-04-18 | Done | Low | 8
8 | BA_John | Business Analyst | Stakeholder workshop: A/B Testing Framework | Business Analyst task for 'A/B Testing Framework'. Deliverable sized to 3 SP. | 2025-04-15 | 2025-04-16 | Done | High | 3
8 | Data_Liam | Data Team | Balance analysis: Season Pass | Data Team task for 'Season Pass'. Deliverable sized to 8 SP. | 2025-04-21 | 2025-04-23 | Done | Low | 8
8 | FE_Noah | Frontend | Animations & VFX: Leaderboard | Frontend task for 'Leaderboard'. Deliverable sized to 3 SP. | 2025-04-15 | 2025-04-17 | Done | Medium | 3
8 | FE_Emily | Frontend | Implement UI: Cloud Save | Frontend task for 'Cloud Save'. Deliverable sized to 5 SP. | 2025-04-20 | 2025-04-23 | Done | Medium | 5
8 | FE_David | Frontend | UX polish: Obstacle Library | Frontend task for 'Obstacle Library'. Deliverable sized to 8 SP. | 2025-04-14 | 2025-04-18 | Done | Medium | 8
8 | FE_Emily | Frontend | UI integration test fixes: Weekly Boss Chase | Frontend task for 'Weekly Boss Chase'. Deliverable sized to 5 SP. | 2025-04-22 | 2025-04-24 | Done | Medium | 5
8 | FE_Noah | Frontend | Animations & VFX: Social Sharing | Frontend task for 'Social Sharing'. Deliverable sized to 5 SP. | 2025-04-18 | 2025-04-19 | Done | High | 5
8 | QA_Olivia | QA | Test data setup: Season Pass | QA task for 'Season Pass'. Deliverable sized to 8 SP. | 2025-04-18 | 2025-04-23 | Done | Low | 8
8 | QA_Daniel | QA | Functional test: Offline Mode | QA task for 'Offline Mode'. Deliverable sized to 5 SP. | 2025-04-18 | 2025-04-19 | Done | Low | 5
8 | QA_Daniel | QA | Functional test: Live Ops Tooling | QA task for 'Live Ops Tooling'. Deliverable sized to 5 SP. | 2025-04-20 | 2025-04-21 | Done | Medium | 5
9 | BE_Ava | Backend | Authentication/Session: Live Ops Tooling | Backend task for 'Live Ops Tooling'. Deliverable sized to 8 SP. | 2025-05-01 | 2025-05-03 | Done | Medium | 8
9 | BE_Sophia | Backend | API endpoint: Shop & IAP | Backend task for 'Shop & IAP'. Deliverable sized to 3 SP. | 2025-05-05 | 2025-05-06 | Done | Medium | 3
9 | BE_Sophia | Backend | API endpoint: Guilds & Chat | Backend task for 'Guilds & Chat'. Deliverable sized to 3 SP. | 2025-04-30 | 2025-05-02 | Done | High | 3
9 | BE_Sophia | Backend | API endpoint: Character Customization | Backend task for 'Character Customization'. Deliverable sized to 3 SP. | 2025-05-05 | 2025-05-07 | Done | Medium | 3
9 | BE_Michael | Backend | Leaderboard/Guild service: Accessibility | Backend task for 'Accessibility'. Deliverable sized to 5 SP. | 2025-05-06 | 2025-05-07 | Done | Medium | 5
9 | BE_Michael | Backend | Performance tuning: Shop & IAP | Backend task for 'Shop & IAP'. Deliverable sized to 5 SP. | 2025-05-04 | 2025-05-06 | Done | Medium | 5
9 | BA_John | Business Analyst | User stories: Launch & Post-Launch | Business Analyst task for 'Launch & Post-Launch'. Deliverable sized to 8 SP. | 2025-05-05 | 2025-05-09 | Done | Medium | 8
9 | BA_Alice | Business Analyst | Epic scoping: Leaderboard | Business Analyst task for 'Leaderboard'. Deliverable sized to 5 SP. | 2025-05-01 | 2025-05-02 | Done | Medium | 5
9 | BA_Alice | Business Analyst | User stories: A/B Testing Framework | Business Analyst task for 'A/B Testing Framework'. Deliverable sized to 5 SP. | 2025-05-02 | 2025-05-05 | Done | Low | 5
9 | Data_Liam | Data Team | Event schema: Offline Mode | Data Team task for 'Offline Mode'. Deliverable sized to 8 SP. | 2025-05-05 | 2025-05-08 | Done | Medium | 8
9 | FE_Emily | Frontend | UI integration test fixes: Beta Release | Frontend task for 'Beta Release'. Deliverable sized to 5 SP. | 2025-05-02 | 2025-05-03 | Done | Medium | 5
9 | FE_David | Frontend | UX polish: Shop & IAP | Frontend task for 'Shop & IAP'. Deliverable sized to 3 SP. | 2025-05-01 | 2025-05-03 | Done | Low | 3
9 | FE_Emily | Frontend | UI integration test fixes: Season Pass | Frontend task for 'Season Pass'. Deliverable sized to 3 SP. | 2025-05-07 | 2025-05-09 | Done | High | 3
9 | FE_Noah | Frontend | UX polish: Beta Release | Frontend task for 'Beta Release'. Deliverable sized to 3 SP. | 2025-05-05 | 2025-05-06 | Done | Low | 3
9 | FE_Noah | Frontend | Animations & VFX: Localization | Frontend task for 'Localization'. Deliverable sized to 5 SP. | 2025-05-04 | 2025-05-06 | Done | High | 5
9 | FE_David | Frontend | UI integration test fixes: Shop & IAP | Frontend task for 'Shop & IAP'. Deliverable sized to 5 SP. | 2025-05-06 | 2025-05-08 | Done | Medium | 5
9 | QA_Daniel | QA | Exploratory testing: Launch & Post-Launch | QA task for 'Launch & Post-Launch'. Deliverable sized to 8 SP. | 2025-05-05 | 2025-05-08 | Done | Medium | 8
9 | QA_Olivia | QA | Test data setup: Level Generator | QA task for 'Level Generator'. Deliverable sized to 8 SP. | 2025-04-30 | 2025-05-02 | Done | Medium | 8
10 | BE_Sophia | Backend | Game logic service: Leaderboard | Backend task for 'Leaderboard'. Deliverable sized to 3 SP. | 2025-05-15 | 2025-05-16 | Done | High | 3
10 | BE_Michael | Backend | Authentication/Session: Social Sharing | Backend task for 'Social Sharing'. Deliverable sized to 5 SP. | 2025-05-14 | 2025-05-16 | Done | High | 5
10 | BE_Ava | Backend | Game logic service: Accessibility | Backend task for 'Accessibility'. Deliverable sized to 8 SP. | 2025-05-18 | 2025-05-22 | Done | Low | 8
10 | BE_Sophia | Backend | Game logic service: Localization | Backend task for 'Localization'. Deliverable sized to 5 SP. | 2025-05-13 | 2025-05-15 | Done | Medium | 5
10 | BE_Michael | Backend | Authentication/Session: Push Notifications | Backend task for 'Push Notifications'. Deliverable sized to 3 SP. | 2025-05-17 | 2025-05-18 | Done | Medium | 3
10 | BA_Alice | Business Analyst | Epic scoping: Beta Release | Business Analyst task for 'Beta Release'. Deliverable sized to 5 SP. | 2025-05-16 | 2025-05-18 | Done | Medium | 5
10 | BA_John | Business Analyst | Backlog refinement: Push Notifications | Business Analyst task for 'Push Notifications'. Deliverable sized to 3 SP. | 2025-05-14 | 2025-05-15 | Done | Medium | 3
10 | BA_Alice | Business Analyst | User stories: Character Customization | Business Analyst task for 'Character Customization'. Deliverable sized to 3 SP. | 2025-05-20 | 2025-05-22 | Done | Medium | 3
10 | BA_John | Business Analyst | Backlog refinement: Obstacle Library | Business Analyst task for 'Obstacle Library'. Deliverable sized to 5 SP. | 2025-05-18 | 2025-05-21 | Done | Medium | 5
10 | Data_Liam | Data Team | A/B experiment design: Weekly Boss Chase | Data Team task for 'Weekly Boss Chase'. Deliverable sized to 3 SP. | 2025-05-18 | 2025-05-20 | Done | Low | 3
10 | Data_Liam | Data Team | Balance analysis: Power-ups & Boosts | Data Team task for 'Power-ups & Boosts'. Deliverable sized to 5 SP. | 2025-05-17 | 2025-05-20 | Done | Medium | 5
10 | FE_Emily | Frontend | Animations & VFX: Crafting & Upgrades | Frontend task for 'Crafting & Upgrades'. Deliverable sized to 5 SP. | 2025-05-13 | 2025-05-14 | Done | Medium | 5
10 | FE_Noah | Frontend | UX polish: Weekly Boss Chase | Frontend task for 'Weekly Boss Chase'. Deliverable sized to 8 SP. | 2025-05-13 | 2025-05-15 | Done | Medium | 8
10 | FE_Emily | Frontend | UI integration test fixes: Inventory | Frontend task for 'Inventory'. Deliverable sized to 3 SP. | 2025-05-16 | 2025-05-18 | Done | Low | 3
10 | FE_David | Frontend | Responsive layout: Launch & Post-Launch | Frontend task for 'Launch & Post-Launch'. Deliverable sized to 3 SP. | 2025-05-15 | 2025-05-17 | Done | Low | 3
10 | FE_David | Frontend | UI integration test fixes: Onboarding & Tutorial | Frontend task for 'Onboarding & Tutorial'. Deliverable sized to 5 SP. | 2025-05-12 | 2025-05-15 | Done | Medium | 5
10 | QA_Olivia | QA | Regression suite update: Guilds & Chat | QA task for 'Guilds & Chat'. Deliverable sized to 8 SP. | 2025-05-16 | 2025-05-21 | Done | Medium | 8
10 | QA_Daniel | QA | Test plan: Weekly Boss Chase | QA task for 'Weekly Boss Chase'. Deliverable sized to 8 SP. | 2025-05-19 | 2025-05-23 | Done | Medium | 8
11 | BE_Michael | Backend | API endpoint: Shop & IAP | Backend task for 'Shop & IAP'. Deliverable sized to 8 SP. | 2025-05-28 | 2025-06-01 | Done | Low | 8
11 | BE_Sophia | Backend | Game logic service: Onboarding & Tutorial | Backend task for 'Onboarding & Tutorial'. Deliverable sized to 8 SP. | 2025-05-26 | 2025-05-30 | Done | High | 8
11 | BE_Ava | Backend | Performance tuning: Social Sharing | Backend task for 'Social Sharing'. Deliverable sized to 3 SP. | 2025-05-27 | 2025-05-29 | Done | Medium | 3
11 | BE_Ava | Backend | API endpoint: Localization | Backend task for 'Localization'. Deliverable sized to 5 SP. | 2025-06-02 | 2025-06-04 | Done | High | 5
11 | BA_John | Business Analyst | Acceptance criteria: A/B Testing Framework | Business Analyst task for 'A/B Testing Framework'. Deliverable sized to 5 SP. | 2025-06-01 | 2025-06-02 | Done | Low | 5
11 | BA_Alice | Business Analyst | Backlog refinement: Onboarding & Tutorial | Business Analyst task for 'Onboarding & Tutorial'. Deliverable sized to 8 SP. | 2025-05-31 | 2025-06-03 | Done | Medium | 8
11 | BA_John | Business Analyst | Acceptance criteria: Core Runner Mechanics | Business Analyst task for 'Core Runner Mechanics'. Deliverable sized to 3 SP. | 2025-06-02 | 2025-06-03 | Done | Low | 3
11 | Data_Liam | Data Team | Balance analysis: Power-ups & Boosts | Data Team task for 'Power-ups & Boosts'. Deliverable sized to 3 SP. | 2025-06-02 | 2025-06-03 | Done | High | 3
11 | Data_Liam | Data Team | A/B experiment design: Core Runner Mechanics | Data Team task for 'Core Runner Mechanics'. Deliverable sized to 3 SP. | 2025-05-30 | 2025-06-01 | Done | Medium | 3
11 | Data_Liam | Data Team | Event schema: Onboarding & Tutorial | Data Team task for 'Onboarding & Tutorial'. Deliverable sized to 3 SP. | 2025-06-02 | 2025-06-04 | Done | Medium | 3
11 | FE_David | Frontend | Implement UI: Level Generator | Frontend task for 'Level Generator'. Deliverable sized to 5 SP. | 2025-06-03 | 2025-06-04 | Done | Medium | 5
11 | FE_David | Frontend | Responsive layout: Core Runner Mechanics | Frontend task for 'Core Runner Mechanics'. Deliverable sized to 5 SP. | 2025-05-29 | 2025-05-30 | Done | High | 5
11 | FE_Noah | Frontend | UX polish: Character Customization | Frontend task for 'Character Customization'. Deliverable sized to 3 SP. | 2025-06-03 | 2025-06-05 | Done | High | 3
11 | FE_Noah | Frontend | UX polish: Accessibility | Frontend task for 'Accessibility'. Deliverable sized to 5 SP. | 2025-05-26 | 2025-05-28 | Done | High | 5
11 | FE_Emily | Frontend | Animations & VFX: Core Runner Mechanics | Frontend task for 'Core Runner Mechanics'. Deliverable sized to 5 SP. | 2025-05-30 | 2025-05-31 | Done | High | 5
11 | FE_Emily | Frontend | Animations & VFX: Launch & Post-Launch | Frontend task for 'Launch & Post-Launch'. Deliverable sized to 5 SP. | 2025-05-27 | 2025-05-30 | Done | Low | 5
11 | QA_Olivia | QA | Regression suite update: Daily Challenges | QA task for 'Daily Challenges'. Deliverable sized to 5 SP. | 2025-05-27 | 2025-05-30 | Done | Medium | 5
11 | QA_Daniel | QA | Functional test: Localization | QA task for 'Localization'. Deliverable sized to 3 SP. | 2025-06-01 | 2025-06-02 | Done | High | 3
11 | QA_Olivia | QA | Test plan: Weekly Boss Chase | QA task for 'Weekly Boss Chase'. Deliverable sized to 5 SP. | 2025-05-31 | 2025-06-01 | Done | Medium | 5
11 | QA_Daniel | QA | Regression suite update: Guilds & Chat | QA task for 'Guilds & Chat'. Deliverable sized to 5 SP. | 2025-06-03 | 2025-06-05 | Done | Medium | 5
12 | BE_Sophia | Backend | Authentication/Session: Live Ops Tooling | Backend task for 'Live Ops Tooling'. Deliverable sized to 5 SP. | 2025-06-09 | 2025-06-10 | Done | Medium | 5
12 | BE_Ava | Backend | Performance tuning: Localization | Backend task for 'Localization'. Deliverable sized to 8 SP. | 2025-06-12 | 2025-06-17 | Done | Medium | 8
12 | BE_Sophia | Backend | Performance tuning: Accessibility | Backend task for 'Accessibility'. Deliverable sized to 5 SP. | 2025-06-17 | 2025-06-18 | Done | Medium | 5
12 | BE_Michael | Backend | API endpoint: Inventory | Backend task for 'Inventory'. Deliverable sized to 5 SP. | 2025-06-11 | 2025-06-12 | Done | Medium | 5
12 | BE_Michael | Backend | API endpoint: Crafting & Upgrades | Backend task for 'Crafting & Upgrades'. Deliverable sized to 5 SP. | 2025-06-11 | 2025-06-14 | Done | Medium | 5
12 | BA_John | Business Analyst | Backlog refinement: Crafting & Upgrades | Business Analyst task for 'Crafting & Upgrades'. Deliverable sized to 5 SP. | 2025-06-17 | 2025-06-19 | Done | Medium | 5
12 | BA_John | Business Analyst | Stakeholder workshop: Cloud Save | Business Analyst task for 'Cloud Save'. Deliverable sized to 5 SP. | 2025-06-10 | 2025-06-13 | Done | Low | 5
12 | BA_Alice | Business Analyst | Epic scoping: Character Customization | Business Analyst task for 'Character Customization'. Deliverable sized to 8 SP. | 2025-06-11 | 2025-06-15 | Done | Medium | 8
12 | Data_Liam | Data Team | Dashboard build: Localization | Data Team task for 'Localization'. Deliverable sized to 5 SP. | 2025-06-10 | 2025-06-11 | Done | Low | 5
12 | Data_Liam | Data Team | A/B experiment design: Accessibility | Data Team task for 'Accessibility'. Deliverable sized to 3 SP. | 2025-06-09 | 2025-06-10 | Done | Medium | 3
12 | FE_Noah | Frontend | Responsive layout: Analytics & Telemetry | Frontend task for 'Analytics & Telemetry'. Deliverable sized to 3 SP. | 2025-06-10 | 2025-06-12 | Done | Medium | 3
12 | FE_Emily | Frontend | Implement UI: Obstacle Library | Frontend task for 'Obstacle Library'. Deliverable sized to 5 SP. | 2025-06-10 | 2025-06-12 | Done | Low | 5
12 | FE_Emily | Frontend | Responsive layout: Localization | Frontend task for 'Localization'. Deliverable sized to 3 SP. | 2025-06-11 | 2025-06-12 | Done | Medium | 3
12 | FE_David | Frontend | Animations & VFX: Power-ups & Boosts | Frontend task for 'Power-ups & Boosts'. Deliverable sized to 5 SP. | 2025-06-14 | 2025-06-17 | Done | High | 5
12 | FE_Noah | Frontend | Animations & VFX: Live Ops Tooling | Frontend task for 'Live Ops Tooling'. Deliverable sized to 5 SP. | 2025-06-12 | 2025-06-13 | Done | Medium | 5
12 | FE_David | Frontend | Implement UI: Leaderboard | Frontend task for 'Leaderboard'. Deliverable sized to 3 SP. | 2025-06-13 | 2025-06-15 | Done | Medium | 3
12 | QA_Olivia | QA | Regression suite update: Leaderboard | QA task for 'Leaderboard'. Deliverable sized to 8 SP. | 2025-06-13 | 2025-06-17 | Done | High | 8
12 | QA_Daniel | QA | Functional test: Analytics & Telemetry | QA task for 'Analytics & Telemetry'. Deliverable sized to 5 SP. | 2025-06-15 | 2025-06-17 | Done | High | 5
12 | QA_Daniel | QA | Regression suite update: Leaderboard | QA task for 'Leaderboard'. Deliverable sized to 5 SP. | 2025-06-16 | 2025-06-18 | Done | Medium | 5
13 | BE_Sophia | Backend | API endpoint: Offline Mode | Backend task for 'Offline Mode'. Deliverable sized to 3 SP. | 2025-07-01 | 2025-07-02 | Done | High | 3
13 | BE_Michael | Backend | Game logic service: Launch & Post-Launch | Backend task for 'Launch & Post-Launch'. Deliverable sized to 5 SP. | 2025-06-26 | 2025-06-27 | Done | Low | 5
13 | BE_Ava | Backend | Leaderboard/Guild service: Obstacle Library | Backend task for 'Obstacle Library'. Deliverable sized to 3 SP. | 2025-06-30 | 2025-07-02 | Done | High | 3
13 | BE_Sophia | Backend | Game logic service: Shop & IAP | Backend task for 'Shop & IAP'. Deliverable sized to 5 SP. | 2025-06-28 | 2025-06-29 | Done | Low | 5
13 | BE_Ava | Backend | Performance tuning: Anti-cheat | Backend task for 'Anti-cheat'. Deliverable sized to 3 SP. | 2025-06-28 | 2025-06-30 | Done | Low | 3
13 | BE_Michael | Backend | Game logic service: Level Generator | Backend task for 'Level Generator'. Deliverable sized to 5 SP. | 2025-06-25 | 2025-06-28 | Done | Low | 5
13 | BE_Ava | Backend | Leaderboard/Guild service: Offline Mode | Backend task for 'Offline Mode'. Deliverable sized to 3 SP. | 2025-06-30 | 2025-07-02 | Done | Medium | 3
13 | BA_John | Business Analyst | Acceptance criteria: Live Ops Tooling | Business Analyst task for 'Live Ops Tooling'. Deliverable sized to 5 SP. | 2025-06-23 | 2025-06-24 | Done | Medium | 5
13 | BA_Alice | Business Analyst | Stakeholder workshop: Guilds & Chat | Business Analyst task for 'Guilds & Chat'. Deliverable sized to 5 SP. | 2025-06-27 | 2025-06-28 | Done | High | 5
13 | BA_John | Business Analyst | Epic scoping: Cloud Save | Business Analyst task for 'Cloud Save'. Deliverable sized to 3 SP. | 2025-06-23 | 2025-06-24 | Done | Medium | 3
13 | BA_Alice | Business Analyst | Acceptance criteria: Power-ups & Boosts | Business Analyst task for 'Power-ups & Boosts'. Deliverable sized to 3 SP. | 2025-06-29 | 2025-06-30 | Done | Medium | 3
13 | Data_Liam | Data Team | Dashboard build: Inventory | Data Team task for 'Inventory'. Deliverable sized to 3 SP. | 2025-06-24 | 2025-06-25 | Done | Medium | 3
13 | Data_Liam | Data Team | Dashboard build: Obstacle Library | Data Team task for 'Obstacle Library'. Deliverable sized to 5 SP. | 2025-06-30 | 2025-07-02 | Done | Low | 5
13 | FE_David | Frontend | Responsive layout: Leaderboard | Frontend task for 'Leaderboard'. Deliverable sized to 5 SP. | 2025-06-24 | 2025-06-26 | Done | Low | 5
13 | FE_Emily | Frontend | Animations & VFX: Onboarding & Tutorial | Frontend task for 'Onboarding & Tutorial'. Deliverable sized to 8 SP. | 2025-06-24 | 2025-06-28 | Done | Medium | 8
13 | FE_Noah | Frontend | UX polish: Power-ups & Boosts | Frontend task for 'Power-ups & Boosts'. Deliverable sized to 8 SP. | 2025-06-29 | 2025-07-04 | Done | Medium | 8
13 | FE_David | Frontend | UX polish: Shop & IAP | Frontend task for 'Shop & IAP'. Deliverable sized to 5 SP. | 2025-06-30 | 2025-07-03 | Done | High | 5
13 | QA_Olivia | QA | Exploratory testing: Character Customization | QA task for 'Character Customization'. Deliverable sized to 5 SP. | 2025-07-01 | 2025-07-04 | Done | Low | 5
13 | QA_Olivia | QA | Regression suite update: Analytics & Telemetry | QA task for 'Analytics & Telemetry'. Deliverable sized to 3 SP. | 2025-06-24 | 2025-06-26 | Done | High | 3
13 | QA_Daniel | QA | Regression suite update: Character Customization | QA task for 'Character Customization'. Deliverable sized to 8 SP. | 2025-06-27 | 2025-07-01 | Done | Low | 8
14 | BE_Ava | Backend | Leaderboard/Guild service: Accessibility | Backend task for 'Accessibility'. Deliverable sized to 5 SP. | 2025-07-15 | 2025-07-18 | Done | Medium | 5
14 | BE_Ava | Backend | Authentication/Session: Level Generator | Backend task for 'Level Generator'. Deliverable sized to 5 SP. | 2025-07-14 | 2025-07-16 | Done | High | 5
14 | BE_Sophia | Backend | Game logic service: Beta Release | Backend task for 'Beta Release'. Deliverable sized to 3 SP. | 2025-07-14 | 2025-07-15 | Done | Medium | 3
14 | BE_Michael | Backend | Performance tuning: Guilds & Chat | Backend task for 'Guilds & Chat'. Deliverable sized to 5 SP. | 2025-07-11 | 2025-07-14 | Done | High | 5
14 | BE_Michael | Backend | Performance tuning: Daily Challenges | Backend task for 'Daily Challenges'. Deliverable sized to 3 SP. | 2025-07-10 | 2025-07-12 | Done | High | 3
14 | BE_Sophia | Backend | Game logic service: Character Customization | Backend task for 'Character Customization'. Deliverable sized to 5 SP. | 2025-07-09 | 2025-07-12 | Done | High | 5
14 | BA_John | Business Analyst | User stories: Core Runner Mechanics | Business Analyst task for 'Core Runner Mechanics'. Deliverable sized to 5 SP. | 2025-07-14 | 2025-07-16 | Done | Medium | 5
14 | BA_Alice | Business Analyst | Epic scoping: Analytics & Telemetry | Business Analyst task for 'Analytics & Telemetry'. Deliverable sized to 5 SP. | 2025-07-14 | 2025-07-17 | Done | Medium | 5
14 | BA_John | Business Analyst | Acceptance criteria: Launch & Post-Launch | Business Analyst task for 'Launch & Post-Launch'. Deliverable sized to 5 SP. | 2025-07-08 | 2025-07-11 | Done | Medium | 5
14 | BA_Alice | Business Analyst | Backlog refinement: Shop & IAP | Business Analyst task for 'Shop & IAP'. Deliverable sized to 3 SP. | 2025-07-14 | 2025-07-15 | Done | High | 3
14 | Data_Liam | Data Team | A/B experiment design: Level Generator | Data Team task for 'Level Generator'. Deliverable sized to 8 SP. | 2025-07-09 | 2025-07-13 | Done | Low | 8
14 | FE_David | Frontend | Animations & VFX: Accessibility | Frontend task for 'Accessibility'. Deliverable sized to 3 SP. | 2025-07-10 | 2025-07-11 | Done | High | 3
14 | FE_Noah | Frontend | Implement UI: Season Pass | Frontend task for 'Season Pass'. Deliverable sized to 8 SP. | 2025-07-07 | 2025-07-11 | Done | High | 8
14 | FE_Emily | Frontend | Responsive layout: Beta Release | Frontend task for 'Beta Release'. Deliverable sized to 3 SP. | 2025-07-09 | 2025-07-10 | Done | Medium | 3
14 | FE_Emily | Frontend | Implement UI: Cloud Save | Frontend task for 'Cloud Save'. Deliverable sized to 5 SP. | 2025-07-11 | 2025-07-14 | Done | Medium | 5
14 | FE_David | Frontend | Responsive layout: Inventory | Frontend task for 'Inventory'. Deliverable sized to 5 SP. | 2025-07-09 | 2025-07-10 | Done | Medium | 5
14 | QA_Daniel | QA | Regression suite update: Core Runner Mechanics | QA task for 'Core Runner Mechanics'. Deliverable sized to 3 SP. | 2025-07-08 | 2025-07-10 | Done | Low | 3
14 | QA_Olivia | QA | Functional test: Live Ops Tooling | QA task for 'Live Ops Tooling'. Deliverable sized to 3 SP. | 2025-07-12 | 2025-07-14 | Done | High | 3
14 | QA_Olivia | QA | Test data setup: Localization | QA task for 'Localization'. Deliverable sized to 5 SP. | 2025-07-09 | 2025-07-11 | Done | Low | 5
14 | QA_Daniel | QA | Exploratory testing: Season Pass | QA task for 'Season Pass'. Deliverable sized to 5 SP. | 2025-07-13 | 2025-07-15 | Done | Medium | 5
15 | BE_Michael | Backend | Authentication/Session: Analytics & Telemetry | Backend task for 'Analytics & Telemetry'. Deliverable sized to 5 SP. | 2025-07-23 | 2025-07-26 | Done | Medium | 5
15 | BE_Michael | Backend | Leaderboard/Guild service: A/B Testing Framework | Backend task for 'A/B Testing Framework'. Deliverable sized to 3 SP. | 2025-07-31 | 2025-08-01 | Done | High | 3
15 | BE_Ava | Backend | Leaderboard/Guild service: Accessibility | Backend task for 'Accessibility'. Deliverable sized to 8 SP. | 2025-07-21 | 2025-07-25 | Done | Low | 8
15 | BE_Sophia | Backend | Authentication/Session: Inventory | Backend task for 'Inventory'. Deliverable sized to 5 SP. | 2025-07-21 | 2025-07-23 | Done | High | 5
15 | BE_Sophia | Backend | Game logic service: Inventory | Backend task for 'Inventory'. Deliverable sized to 5 SP. | 2025-07-22 | 2025-07-25 | Done | Medium | 5
15 | BA_Alice | Business Analyst | Backlog refinement: Power-ups & Boosts | Business Analyst task for 'Power-ups & Boosts'. Deliverable sized to 5 SP. | 2025-07-22 | 2025-07-24 | Done | Low | 5
15 | BA_Alice | Business Analyst | Acceptance criteria: Pet Companions | Business Analyst task for 'Pet Companions'. Deliverable sized to 3 SP. | 2025-07-28 | 2025-07-29 | Done | High | 3
15 | BA_John | Business Analyst | Stakeholder workshop: Daily Challenges | Business Analyst task for 'Daily Challenges'. Deliverable sized to 8 SP. | 2025-07-26 | 2025-07-28 | Done | Medium | 8
15 | Data_Liam | Data Team | Dashboard build: Shop & IAP | Data Team task for 'Shop & IAP'. Deliverable sized to 5 SP. | 2025-07-29 | 2025-07-31 | Done | High | 5
15 | Data_Liam | Data Team | Balance analysis: Analytics & Telemetry | Data Team task for 'Analytics & Telemetry'. Deliverable sized to 5 SP. | 2025-07-25 | 2025-07-26 | Done | High | 5
15 | FE_Noah | Frontend | UX polish: Leaderboard | Frontend task for 'Leaderboard'. Deliverable sized to 5 SP. | 2025-07-22 | 2025-07-25 | Done | High | 5
15 | FE_Emily | Frontend | Implement UI: Power-ups & Boosts | Frontend task for 'Power-ups & Boosts'. Deliverable sized to 5 SP. | 2025-07-24 | 2025-07-26 | Done | Medium | 5
15 | FE_Emily | Frontend | Animations & VFX: Social Sharing | Frontend task for 'Social Sharing'. Deliverable sized to 5 SP. | 2025-07-22 | 2025-07-24 | Done | Low | 5
15 | FE_David | Frontend | UX polish: Anti-cheat | Frontend task for 'Anti-cheat'. Deliverable sized to 3 SP. | 2025-07-23 | 2025-07-25 | Done | Medium | 3
15 | FE_Noah | Frontend | UI integration test fixes: Obstacle Library | Frontend task for 'Obstacle Library'. Deliverable sized to 3 SP. | 2025-07-29 | 2025-07-30 | Done | Medium | 3
15 | FE_David | Frontend | Animations & VFX: Launch & Post-Launch | Frontend task for 'Launch & Post-Launch'. Deliverable sized to 5 SP. | 2025-07-29 | 2025-07-30 | Done | Medium | 5
15 | QA_Daniel | QA | Test plan: Crafting & Upgrades | QA task for 'Crafting & Upgrades'. Deliverable sized to 5 SP. | 2025-07-26 | 2025-07-27 | Done | Low | 5
15 | QA_Daniel | QA | Regression suite update: Power-ups & Boosts | QA task for 'Power-ups & Boosts'. Deliverable sized to 3 SP. | 2025-07-23 | 2025-07-24 | Done | Low | 3
15 | QA_Olivia | QA | Functional test: Launch & Post-Launch | QA task for 'Launch & Post-Launch'. Deliverable sized to 5 SP. | 2025-07-28 | 2025-07-30 | Done | Medium | 5
15 | QA_Olivia | QA | Test plan: Obstacle Library | QA task for 'Obstacle Library'. Deliverable sized to 3 SP. | 2025-07-25 | 2025-07-26 | Done | High | 3
16 | BE_Sophia | Backend | API endpoint: Power-ups & Boosts | Backend task for 'Power-ups & Boosts'. Deliverable sized to 3 SP. | 2025-08-06 | 2025-08-08 | Done | Medium | 3
16 | BE_Sophia | Backend | Leaderboard/Guild service: Inventory | Backend task for 'Inventory'. Deliverable sized to 3 SP. | 2025-08-05 | 2025-08-06 | Done | Medium | 3
16 | BE_Sophia | Backend | Authentication/Session: Crafting & Upgrades | Backend task for 'Crafting & Upgrades'. Deliverable sized to 3 SP. | 2025-08-14 | 2025-08-16 | Done | Low | 3
16 | BE_Michael | Backend | Authentication/Session: Accessibility | Backend task for 'Accessibility'. Deliverable sized to 5 SP. | 2025-08-11 | 2025-08-12 | Done | High | 5
16 | BE_Michael | Backend | Leaderboard/Guild service: Season Pass | Backend task for 'Season Pass'. Deliverable sized to 3 SP. | 2025-08-07 | 2025-08-08 | Done | Low | 3
16 | BE_Ava | Backend | Leaderboard/Guild service: Pet Companions | Backend task for 'Pet Companions'. Deliverable sized to 8 SP. | 2025-08-05 | 2025-08-09 | Done | Medium | 8
16 | BA_John | Business Analyst | Stakeholder workshop: Push Notifications | Business Analyst task for 'Push Notifications'. Deliverable sized to 5 SP. | 2025-08-09 | 2025-08-12 | Done | Medium | 5
16 | BA_Alice | Business Analyst | Epic scoping: Inventory | Business Analyst task for 'Inventory'. Deliverable sized to 8 SP. | 2025-08-09 | 2025-08-13 | Done | Low | 8
16 | BA_John | Business Analyst | Stakeholder workshop: Localization | Business Analyst task for 'Localization'. Deliverable sized to 5 SP. | 2025-08-10 | 2025-08-12 | Done | High | 5
16 | Data_Liam | Data Team | Dashboard build: Season Pass | Data Team task for 'Season Pass'. Deliverable sized to 5 SP. | 2025-08-06 | 2025-08-09 | Done | Medium | 5
16 | Data_Liam | Data Team | ETL pipeline: A/B Testing Framework | Data Team task for 'A/B Testing Framework'. Deliverable sized to 3 SP. | 2025-08-09 | 2025-08-10 | Done | Low | 3
16 | FE_David | Frontend | UX polish: Live Ops Tooling | Frontend task for 'Live Ops Tooling'. Deliverable sized to 3 SP. | 2025-08-04 | 2025-08-05 | Done | High | 3
16 | FE_Emily | Frontend | UI integration test fixes: Inventory | Frontend task for 'Inventory'. Deliverable sized to 3 SP. | 2025-08-10 | 2025-08-12 | Done | Medium | 3
16 | FE_Noah | Frontend | UI integration test fixes: Crafting & Upgrades | Frontend task for 'Crafting & Upgrades'. Deliverable sized to 3 SP. | 2025-08-04 | 2025-08-05 | Done | Medium | 3
16 | FE_Noah | Frontend | Implement UI: Character Customization | Frontend task for 'Character Customization'. Deliverable sized to 5 SP. | 2025-08-07 | 2025-08-10 | Done | Medium | 5
16 | FE_David | Frontend | Animations & VFX: Live Ops Tooling | Frontend task for 'Live Ops Tooling'. Deliverable sized to 5 SP. | 2025-08-09 | 2025-08-12 | Done | High | 5
16 | FE_Emily | Frontend | Responsive layout: Guilds & Chat | Frontend task for 'Guilds & Chat'. Deliverable sized to 5 SP. | 2025-08-11 | 2025-08-12 | Done | Medium | 5
16 | QA_Olivia | QA | Regression suite update: Obstacle Library | QA task for 'Obstacle Library'. Deliverable sized to 8 SP. | 2025-08-08 | 2025-08-12 | Done | Medium | 8
16 | QA_Daniel | QA | Test plan: Leaderboard | QA task for 'Leaderboard'. Deliverable sized to 8 SP. | 2025-08-10 | 2025-08-13 | Done | Medium | 8
17 | BE_Michael | Backend | Game logic service: Push Notifications | Backend task for 'Push Notifications'. Deliverable sized to 5 SP. | 2025-08-24 | 2025-08-26 | Done | Medium | 5
17 | BE_Sophia | Backend | Performance tuning: Core Runner Mechanics | Backend task for 'Core Runner Mechanics'. Deliverable sized to 8 SP. | 2025-08-22 | 2025-08-25 | Done | High | 8
17 | BE_Michael | Backend | Performance tuning: Push Notifications | Backend task for 'Push Notifications'. Deliverable sized to 5 SP. | 2025-08-22 | 2025-08-25 | Done | High | 5
17 | BE_Ava | Backend | Leaderboard/Guild service: Leaderboard | Backend task for 'Leaderboard'. Deliverable sized to 5 SP. | 2025-08-25 | 2025-08-26 | Done | Medium | 5
17 | BE_Ava | Backend | Authentication/Session: Character Customization | Backend task for 'Character Customization'. Deliverable sized to 3 SP. | 2025-08-23 | 2025-08-25 | Done | High | 3
17 | BA_John | Business Analyst | Stakeholder workshop: A/B Testing Framework | Business Analyst task for 'A/B Testing Framework'. Deliverable sized to 3 SP. | 2025-08-26 | 2025-08-28 | Done | High | 3
17 | BA_John | Business Analyst | User stories: Analytics & Telemetry | Business Analyst task for 'Analytics & Telemetry'. Deliverable sized to 5 SP. | 2025-08-19 | 2025-08-20 | Done | Medium | 5
17 | BA_Alice | Business Analyst | User stories: Character Customization | Business Analyst task for 'Character Customization'. Deliverable sized to 8 SP. | 2025-08-25 | 2025-08-27 | Done | Medium | 8
17 | Data_Liam | Data Team | A/B experiment design: Inventory | Data Team task for 'Inventory'. Deliverable sized to 8 SP. | 2025-08-19 | 2025-08-23 | Done | Low | 8
17 | FE_Noah | Frontend | UX polish: Offline Mode | Frontend task for 'Offline Mode'. Deliverable sized to 5 SP. | 2025-08-20 | 2025-08-21 | Done | Medium | 5
17 | FE_Noah | Frontend | UI integration test fixes: Localization | Frontend task for 'Localization'. Deliverable sized to 3 SP. | 2025-08-23 | 2025-08-24 | Done | High | 3
17 | FE_David | Frontend | UI integration test fixes: Offline Mode | Frontend task for 'Offline Mode'. Deliverable sized to 8 SP. | 2025-08-22 | 2025-08-25 | Done | Medium | 8
17 | FE_Emily | Frontend | UX polish: A/B Testing Framework | Frontend task for 'A/B Testing Framework'. Deliverable sized to 8 SP. | 2025-08-23 | 2025-08-27 | Done | High | 8
17 | QA_Olivia | QA | Test plan: Social Sharing | QA task for 'Social Sharing'. Deliverable sized to 8 SP. | 2025-08-19 | 2025-08-22 | Done | Medium | 8
17 | QA_Daniel | QA | Functional test: Inventory | QA task for 'Inventory'. Deliverable sized to 3 SP. | 2025-08-26 | 2025-08-27 | Done | High | 3
17 | QA_Daniel | QA | Test plan: Shop & IAP | QA task for 'Shop & IAP'. Deliverable sized to 5 SP. | 2025-08-25 | 2025-08-27 | Done | Medium | 5
18 | BE_Michael | Backend | Authentication/Session: Localization | Backend task for 'Localization'. Deliverable sized to 3 SP. | 2025-09-10 | 2025-09-12 | Done | Medium | 3
18 | BE_Sophia | Backend | Leaderboard/Guild service: Shop & IAP | Backend task for 'Shop & IAP'. Deliverable sized to 8 SP. | 2025-09-08 | 2025-09-11 | Done | Medium | 8
18 | BE_Michael | Backend | Authentication/Session: Cloud Save | Backend task for 'Cloud Save'. Deliverable sized to 5 SP. | 2025-09-03 | 2025-09-05 | Done | High | 5
18 | BE_Ava | Backend | API endpoint: Live Ops Tooling | Backend task for 'Live Ops Tooling'. Deliverable sized to 3 SP. | 2025-09-07 | 2025-09-09 | Done | High | 3
18 | BE_Ava | Backend | Authentication/Session: Anti-cheat | Backend task for 'Anti-cheat'. Deliverable sized to 5 SP. | 2025-09-08 | 2025-09-09 | Done | Medium | 5
18 | BA_John | Business Analyst | Acceptance criteria: Anti-cheat | Business Analyst task for 'Anti-cheat'. Deliverable sized to 3 SP. | 2025-09-04 | 2025-09-05 | Done | Medium | 3
18 | BA_John | Business Analyst | Stakeholder workshop: Social Sharing | Business Analyst task for 'Social Sharing'. Deliverable sized to 3 SP. | 2025-09-08 | 2025-09-10 | Done | Medium | 3
18 | BA_Alice | Business Analyst | User stories: Guilds & Chat | Business Analyst task for 'Guilds & Chat'. Deliverable sized to 8 SP. | 2025-09-03 | 2025-09-05 | Done | Low | 8
18 | BA_John | Business Analyst | Stakeholder workshop: Cloud Save | Business Analyst task for 'Cloud Save'. Deliverable sized to 3 SP. | 2025-09-04 | 2025-09-05 | Done | High | 3
18 | Data_Liam | Data Team | A/B experiment design: Onboarding & Tutorial | Data Team task for 'Onboarding & Tutorial'. Deliverable sized to 5 SP. | 2025-09-08 | 2025-09-10 | Done | High | 5
18 | Data_Liam | Data Team | A/B experiment design: Beta Release | Data Team task for 'Beta Release'. Deliverable sized to 5 SP. | 2025-09-04 | 2025-09-07 | Done | Low | 5
18 | FE_Emily | Frontend | Implement UI: Season Pass | Frontend task for 'Season Pass'. Deliverable sized to 3 SP. | 2025-09-07 | 2025-09-09 | Done | High | 3
18 | FE_David | Frontend | UI integration test fixes: Cloud Save | Frontend task for 'Cloud Save'. Deliverable sized to 8 SP. | 2025-09-02 | 2025-09-05 | Done | High | 8
18 | FE_Noah | Frontend | Animations & VFX: Social Sharing | Frontend task for 'Social Sharing'. Deliverable sized to 5 SP. | 2025-09-09 | 2025-09-10 | Done | Low | 5
18 | FE_Emily | Frontend | Implement UI: Crafting & Upgrades | Frontend task for 'Crafting & Upgrades'. Deliverable sized to 5 SP. | 2025-09-09 | 2025-09-10 | Done | Medium | 5
18 | FE_Noah | Frontend | UI integration test fixes: Shop & IAP | Frontend task for 'Shop & IAP'. Deliverable sized to 5 SP. | 2025-09-06 | 2025-09-07 | Done | Low | 5
18 | QA_Daniel | QA | Test data setup: Crafting & Upgrades | QA task for 'Crafting & Upgrades'. Deliverable sized to 8 SP. | 2025-09-08 | 2025-09-11 | Done | Low | 8
18 | QA_Olivia | QA | Test data setup: Push Notifications | QA task for 'Push Notifications'. Deliverable sized to 5 SP. | 2025-09-08 | 2025-09-10 | Done | Medium | 5
18 | QA_Olivia | QA | Exploratory testing: Power-ups & Boosts | QA task for 'Power-ups & Boosts'. Deliverable sized to 3 SP. | 2025-09-03 | 2025-09-05 | Done | Medium | 3
19 | BE_Ava | Backend | Game logic service: Launch & Post-Launch | Backend task for 'Launch & Post-Launch'. Deliverable sized to 5 SP. | 2025-09-15 | 2025-09-17 | Done | High | 5
19 | BE_Michael | Backend | Authentication/Session: Season Pass | Backend task for 'Season Pass'. Deliverable sized to 5 SP. | 2025-09-19 | 2025-09-22 | Done | Low | 5
19 | BE_Sophia | Backend | Game logic service: Offline Mode | Backend task for 'Offline Mode'. Deliverable sized to 5 SP. | 2025-09-15 | 2025-09-16 | Done | Medium | 5
19 | BE_Michael | Backend | Leaderboard/Guild service: Leaderboard | Backend task for 'Leaderboard'. Deliverable sized to 5 SP. | 2025-09-22 | 2025-09-25 | Done | Low | 5
19 | BE_Sophia | Backend | Leaderboard/Guild service: A/B Testing Framework | Backend task for 'A/B Testing Framework'. Deliverable sized to 3 SP. | 2025-09-16 | 2025-09-17 | Done | Low | 3
19 | BE_Ava | Backend | Performance tuning: Daily Challenges | Backend task for 'Daily Challenges'. Deliverable sized to 5 SP. | 2025-09-15 | 2025-09-16 | Done | Medium | 5
19 | BA_Alice | Business Analyst | Epic scoping: Daily Challenges | Business Analyst task for 'Daily Challenges'. Deliverable sized to 3 SP. | 2025-09-24 | 2025-09-25 | Done | Low | 3
19 | BA_John | Business Analyst | User stories: Leaderboard | Business Analyst task for 'Leaderboard'. Deliverable sized to 5 SP. | 2025-09-21 | 2025-09-24 | Done | High | 5
19 | BA_John | Business Analyst | Epic scoping: Push Notifications | Business Analyst task for 'Push Notifications'. Deliverable sized to 3 SP. | 2025-09-17 | 2025-09-18 | Done | Medium | 3
19 | BA_Alice | Business Analyst | Backlog refinement: Localization | Business Analyst task for 'Localization'. Deliverable sized to 5 SP. | 2025-09-21 | 2025-09-22 | Done | High | 5
19 | Data_Liam | Data Team | Dashboard build: Localization | Data Team task for 'Localization'. Deliverable sized to 8 SP. | 2025-09-15 | 2025-09-17 | Done | Medium | 8
19 | FE_Noah | Frontend | Implement UI: Character Customization | Frontend task for 'Character Customization'. Deliverable sized to 3 SP. | 2025-09-24 | 2025-09-25 | Done | Low | 3
19 | FE_Emily | Frontend | Responsive layout: Push Notifications | Frontend task for 'Push Notifications'. Deliverable sized to 5 SP. | 2025-09-22 | 2025-09-24 | Done | Medium | 5
19 | FE_Emily | Frontend | Responsive layout: Beta Release | Frontend task for 'Beta Release'. Deliverable sized to 5 SP. | 2025-09-19 | 2025-09-20 | Done | Medium | 5
19 | FE_Noah | Frontend | UI integration test fixes: Launch & Post-Launch | Frontend task for 'Launch & Post-Launch'. Deliverable sized to 5 SP. | 2025-09-19 | 2025-09-22 | Done | Medium | 5
19 | FE_David | Frontend | Implement UI: A/B Testing Framework | Frontend task for 'A/B Testing Framework'. Deliverable sized to 5 SP. | 2025-09-20 | 2025-09-22 | Done | Medium | 5
19 | FE_David | Frontend | Responsive layout: Crafting & Upgrades | Frontend task for 'Crafting & Upgrades'. Deliverable sized to 5 SP. | 2025-09-17 | 2025-09-19 | Done | Low | 5
19 | QA_Daniel | QA | Test data setup: Push Notifications | QA task for 'Push Notifications'. Deliverable sized to 3 SP. | 2025-09-21 | 2025-09-23 | Done | High | 3
19 | QA_Daniel | QA | Regression suite update: Localization | QA task for 'Localization'. Deliverable sized to 3 SP. | 2025-09-24 | 2025-09-26 | Done | Low | 3
19 | QA_Olivia | QA | Regression suite update: Analytics & Telemetry | QA task for 'Analytics & Telemetry'. Deliverable sized to 8 SP. | 2025-09-18 | 2025-09-22 | Done | High | 8
19 | QA_Daniel | QA | Test data setup: Guilds & Chat | QA task for 'Guilds & Chat'. Deliverable sized to 3 SP. | 2025-09-20 | 2025-09-22 | Done | Medium | 3
20 | BE_Ava | Backend | Authentication/Session: Crafting & Upgrades | Backend task for 'Crafting & Upgrades'. Deliverable sized to 5 SP. | 2025-09-29 | 2025-10-02 | In Progress | Low | 5
20 | BE_Sophia | Backend | Performance tuning: Anti-cheat | Backend task for 'Anti-cheat'. Deliverable sized to 5 SP. | 2025-10-01 | 2025-10-02 | In Progress | Medium | 5
20 | BE_Ava | Backend | API endpoint: Obstacle Library | Backend task for 'Obstacle Library'. Deliverable sized to 5 SP. | 2025-10-05 | 2025-10-07 | In Progress | Medium | 5
20 | BE_Michael | Backend | API endpoint: Guilds & Chat | Backend task for 'Guilds & Chat'. Deliverable sized to 5 SP. | 2025-10-06 | 2025-10-07 | In Progress | Medium | 5
20 | BE_Sophia | Backend | Leaderboard/Guild service: Social Sharing | Backend task for 'Social Sharing'. Deliverable sized to 3 SP. | 2025-09-30 | 2025-10-01 | Done | Medium | 3
20 | BE_Michael | Backend | Performance tuning: Guilds & Chat | Backend task for 'Guilds & Chat'. Deliverable sized to 5 SP. | 2025-09-29 | 2025-10-02 | In Progress | Medium | 5
20 | BA_John | Business Analyst | Acceptance criteria: Localization | Business Analyst task for 'Localization'. Deliverable sized to 3 SP. | 2025-10-03 | 2025-10-04 | In Progress | Low | 3
20 | BA_Alice | Business Analyst | Acceptance criteria: Shop & IAP | Business Analyst task for 'Shop & IAP'. Deliverable sized to 5 SP. | 2025-10-06 | 2025-10-09 | In Progress | Medium | 5
20 | BA_John | Business Analyst | Stakeholder workshop: Localization | Business Analyst task for 'Localization'. Deliverable sized to 5 SP. | 2025-10-03 | 2025-10-06 | In Progress | Low | 5
20 | BA_Alice | Business Analyst | User stories: Push Notifications | Business Analyst task for 'Push Notifications'. Deliverable sized to 5 SP. | 2025-10-07 | 2025-10-09 | In Progress | Medium | 5
20 | Data_Liam | Data Team | ETL pipeline: Accessibility | Data Team task for 'Accessibility'. Deliverable sized to 3 SP. | 2025-10-09 | 2025-10-11 | In Progress | Medium | 3
20 | Data_Liam | Data Team | Balance analysis: Obstacle Library | Data Team task for 'Obstacle Library'. Deliverable sized to 5 SP. | 2025-09-29 | 2025-10-01 | Done | Medium | 5
20 | FE_David | Frontend | UX polish: Push Notifications | Frontend task for 'Push Notifications'. Deliverable sized to 3 SP. | 2025-10-06 | 2025-10-08 | In Progress | Medium | 3
20 | FE_David | Frontend | Animations & VFX: Analytics & Telemetry | Frontend task for 'Analytics & Telemetry'. Deliverable sized to 3 SP. | 2025-10-07 | 2025-10-08 | In Progress | High | 3
20 | FE_David | Frontend | UI integration test fixes: Inventory | Frontend task for 'Inventory'. Deliverable sized to 3 SP. | 2025-10-02 | 2025-10-03 | In Progress | High | 3
20 | FE_Noah | Frontend | Implement UI: Inventory | Frontend task for 'Inventory'. Deliverable sized to 3 SP. | 2025-10-08 | 2025-10-09 | In Progress | Low | 3
20 | FE_Noah | Frontend | Implement UI: Beta Release | Frontend task for 'Beta Release'. Deliverable sized to 5 SP. | 2025-10-07 | 2025-10-09 | In Progress | Medium | 5
20 | FE_Emily | Frontend | UI integration test fixes: Live Ops Tooling | Frontend task for 'Live Ops Tooling'. Deliverable sized to 8 SP. | 2025-10-03 | 2025-10-05 | In Progress | Medium | 8
20 | QA_Olivia | QA | Functional test: Inventory | QA task for 'Inventory'. Deliverable sized to 3 SP. | 2025-09-29 | 2025-09-30 | Done | Medium | 3
20 | QA_Daniel | QA | Exploratory testing: Launch & Post-Launch | QA task for 'Launch & Post-Launch'. Deliverable sized to 5 SP. | 2025-10-07 | 2025-10-09 | In Progress | Low | 5
20 | QA_Olivia | QA | Regression suite update: Onboarding & Tutorial | QA task for 'Onboarding & Tutorial'. Deliverable sized to 3 SP. | 2025-10-05 | 2025-10-06 | In Progress | Medium | 3
20 | QA_Daniel | QA | Test plan: Live Ops Tooling | QA task for 'Live Ops Tooling'. Deliverable sized to 5 SP. | 2025-10-01 | 2025-10-02 | In Progress | Medium | 5
20 | QA_Olivia | QA | Regression suite update: Weekly Boss Chase | QA task for 'Weekly Boss Chase'. Deliverable sized to 3 SP. | 2025-10-03 | 2025-10-04 | In Progress | Medium | 3
21 | BE_Sophia | Backend | Performance tuning: Crafting & Upgrades | Backend task for 'Crafting & Upgrades'. Deliverable sized to 5 SP. | 2025-10-18 | 2025-10-21 | To Do | Medium | 5
21 | BE_Sophia | Backend | Authentication/Session: Character Customization | Backend task for 'Character Customization'. Deliverable sized to 5 SP. | 2025-10-19 | 2025-10-20 | To Do | High | 5
21 | BE_Michael | Backend | Game logic service: Season Pass | Backend task for 'Season Pass'. Deliverable sized to 5 SP. | 2025-10-20 | 2025-10-21 | To Do | Medium | 5
21 | BE_Ava | Backend | API endpoint: Shop & IAP | Backend task for 'Shop & IAP'. Deliverable sized to 8 SP. | 2025-10-20 | 2025-10-24 | To Do | Low | 8
21 | BE_Michael | Backend | Performance tuning: Leaderboard | Backend task for 'Leaderboard'. Deliverable sized to 5 SP. | 2025-10-21 | 2025-10-22 | To Do | Medium | 5
21 | BA_Alice | Business Analyst | User stories: Analytics & Telemetry | Business Analyst task for 'Analytics & Telemetry'. Deliverable sized to 3 SP. | 2025-10-23 | 2025-10-25 | To Do | Low | 3
21 | BA_John | Business Analyst | Stakeholder workshop: Analytics & Telemetry | Business Analyst task for 'Analytics & Telemetry'. Deliverable sized to 3 SP. | 2025-10-21 | 2025-10-23 | To Do | High | 3
21 | BA_John | Business Analyst | Backlog refinement: Crafting & Upgrades | Business Analyst task for 'Crafting & Upgrades'. Deliverable sized to 3 SP. | 2025-10-15 | 2025-10-16 | In Progress | High | 3
21 | BA_John | Business Analyst | Epic scoping: Accessibility | Business Analyst task for 'Accessibility'. Deliverable sized to 3 SP. | 2025-10-17 | 2025-10-19 | To Do | Medium | 3
21 | BA_Alice | Business Analyst | Stakeholder workshop: Crafting & Upgrades | Business Analyst task for 'Crafting & Upgrades'. Deliverable sized to 5 SP. | 2025-10-14 | 2025-10-17 | To Do | High | 5
21 | Data_Liam | Data Team | A/B experiment design: Accessibility | Data Team task for 'Accessibility'. Deliverable sized to 3 SP. | 2025-10-23 | 2025-10-24 | To Do | Medium | 3
21 | Data_Liam | Data Team | Balance analysis: Weekly Boss Chase | Data Team task for 'Weekly Boss Chase'. Deliverable sized to 5 SP. | 2025-10-13 | 2025-10-14 | In Progress | Low | 5
21 | FE_Emily | Frontend | Implement UI: Level Generator | Frontend task for 'Level Generator'. Deliverable sized to 3 SP. | 2025-10-15 | 2025-10-17 | To Do | Low | 3
21 | FE_David | Frontend | UI integration test fixes: Anti-cheat | Frontend task for 'Anti-cheat'. Deliverable sized to 5 SP. | 2025-10-18 | 2025-10-19 | To Do | Medium | 5
21 | FE_Noah | Frontend | UX polish: Anti-cheat | Frontend task for 'Anti-cheat'. Deliverable sized to 8 SP. | 2025-10-19 | 2025-10-24 | To Do | Low | 8
21 | FE_David | Frontend | UI integration test fixes: Character Customization | Frontend task for 'Character Customization'. Deliverable sized to 3 SP. | 2025-10-16 | 2025-10-18 | To Do | Medium | 3
21 | FE_Emily | Frontend | Implement UI: Localization | Frontend task for 'Localization'. Deliverable sized to 5 SP. | 2025-10-19 | 2025-10-21 | To Do | Low | 5
21 | QA_Daniel | QA | Functional test: Inventory | QA task for 'Inventory'. Deliverable sized to 8 SP. | 2025-10-17 | 2025-10-20 | To Do | High | 8
21 | QA_Olivia | QA | Exploratory testing: Beta Release | QA task for 'Beta Release'. Deliverable sized to 5 SP. | 2025-10-13 | 2025-10-14 | In Progress | Low | 5
21 | QA_Olivia | QA | Test data setup: Power-ups & Boosts | QA task for 'Power-ups & Boosts'. Deliverable sized to 3 SP. | 2025-10-13 | 2025-10-15 | In Progress | Medium | 3
22 | BE_Sophia | Backend | Performance tuning: Onboarding & Tutorial | Backend task for 'Onboarding & Tutorial'. Deliverable sized to 3 SP. | 2025-11-04 | 2025-11-06 | To Do | Low | 3
22 | BE_Ava | Backend | Performance tuning: Cloud Save | Backend task for 'Cloud Save'. Deliverable sized to 8 SP. | 2025-10-31 | 2025-11-04 | To Do | Medium | 8
22 | BE_Michael | Backend | API endpoint: Season Pass | Backend task for 'Season Pass'. Deliverable sized to 5 SP. | 2025-11-04 | 2025-11-07 | To Do | Medium | 5
22 | BE_Michael | Backend | Game logic service: Beta Release | Backend task for 'Beta Release'. Deliverable sized to 3 SP. | 2025-10-28 | 2025-10-29 | To Do | Medium | 3
22 | BE_Sophia | Backend | Performance tuning: Cloud Save | Backend task for 'Cloud Save'. Deliverable sized to 5 SP. | 2025-11-03 | 2025-11-06 | To Do | Medium | 5
22 | BA_Alice | Business Analyst | User stories: Onboarding & Tutorial | Business Analyst task for 'Onboarding & Tutorial'. Deliverable sized to 5 SP. | 2025-10-30 | 2025-11-02 | To Do | Low | 5
22 | BA_Alice | Business Analyst | Stakeholder workshop: Accessibility | Business Analyst task for 'Accessibility'. Deliverable sized to 3 SP. | 2025-10-30 | 2025-10-31 | To Do | Medium | 3
22 | BA_John | Business Analyst | Acceptance criteria: Shop & IAP | Business Analyst task for 'Shop & IAP'. Deliverable sized to 8 SP. | 2025-11-02 | 2025-11-07 | To Do | Medium | 8
22 | Data_Liam | Data Team | Balance analysis: Crafting & Upgrades | Data Team task for 'Crafting & Upgrades'. Deliverable sized to 5 SP. | 2025-10-30 | 2025-11-02 | To Do | Low | 5
22 | Data_Liam | Data Team | Event schema: Live Ops Tooling | Data Team task for 'Live Ops Tooling'. Deliverable sized to 3 SP. | 2025-11-06 | 2025-11-07 | To Do | Low | 3
22 | FE_David | Frontend | Responsive layout: Localization | Frontend task for 'Localization'. Deliverable sized to 3 SP. | 2025-10-29 | 2025-10-30 | To Do | Medium | 3
22 | FE_Noah | Frontend | UX polish: Offline Mode | Frontend task for 'Offline Mode'. Deliverable sized to 3 SP. | 2025-10-28 | 2025-10-29 | To Do | Low | 3
22 | FE_David | Frontend | Responsive layout: Shop & IAP | Frontend task for 'Shop & IAP'. Deliverable sized to 3 SP. | 2025-11-03 | 2025-11-05 | To Do | Medium | 3
22 | FE_Emily | Frontend | UI integration test fixes: Crafting & Upgrades | Frontend task for 'Crafting & Upgrades'. Deliverable sized to 8 SP. | 2025-10-30 | 2025-11-04 | To Do | Medium | 8
22 | FE_David | Frontend | UX polish: Push Notifications | Frontend task for 'Push Notifications'. Deliverable sized to 3 SP. | 2025-11-04 | 2025-11-05 | To Do | Medium | 3
22 | FE_Noah | Frontend | Implement UI: Launch & Post-Launch | Frontend task for 'Launch & Post-Launch'. Deliverable sized to 5 SP. | 2025-10-27 | 2025-10-29 | To Do | Low | 5
22 | QA_Daniel | QA | Exploratory testing: Social Sharing | QA task for 'Social Sharing'. Deliverable sized to 5 SP. | 2025-11-03 | 2025-11-04 | To Do | High | 5
22 | QA_Olivia | QA | Functional test: Daily Challenges | QA task for 'Daily Challenges'. Deliverable sized to 5 SP. | 2025-10-27 | 2025-10-29 | To Do | Medium | 5
22 | QA_Olivia | QA | Test data setup: Anti-cheat | QA task for 'Anti-cheat'. Deliverable sized to 3 SP. | 2025-11-02 | 2025-11-04 | To Do | Low | 3
22 | QA_Daniel | QA | Exploratory testing: Localization | QA task for 'Localization'. Deliverable sized to 3 SP. | 2025-11-01 | 2025-11-02 | To Do | Medium | 3
23 | BE_Ava | Backend | Authentication/Session: Beta Release | Backend task for 'Beta Release'. Deliverable sized to 3 SP. | 2025-11-16 | 2025-11-17 | To Do | Medium | 3
23 | BE_Michael | Backend | Game logic service: Obstacle Library | Backend task for 'Obstacle Library'. Deliverable sized to 8 SP. | 2025-11-16 | 2025-11-21 | To Do | Medium | 8
23 | BE_Sophia | Backend | Authentication/Session: Onboarding & Tutorial | Backend task for 'Onboarding & Tutorial'. Deliverable sized to 5 SP. | 2025-11-17 | 2025-11-19 | To Do | High | 5
23 | BE_Sophia | Backend | Leaderboard/Guild service: Localization | Backend task for 'Localization'. Deliverable sized to 5 SP. | 2025-11-15 | 2025-11-17 | To Do | Low | 5
23 | BE_Ava | Backend | Authentication/Session: Obstacle Library | Backend task for 'Obstacle Library'. Deliverable sized to 5 SP. | 2025-11-18 | 2025-11-19 | To Do | Medium | 5
23 | BA_John | Business Analyst | Backlog refinement: A/B Testing Framework | Business Analyst task for 'A/B Testing Framework'. Deliverable sized to 5 SP. | 2025-11-17 | 2025-11-19 | To Do | Low | 5
23 | BA_Alice | Business Analyst | Epic scoping: Core Runner Mechanics | Business Analyst task for 'Core Runner Mechanics'. Deliverable sized to 5 SP. | 2025-11-12 | 2025-11-13 | To Do | Medium | 5
23 | BA_Alice | Business Analyst | Acceptance criteria: Leaderboard | Business Analyst task for 'Leaderboard'. Deliverable sized to 3 SP. | 2025-11-19 | 2025-11-20 | To Do | High | 3
23 | BA_John | Business Analyst | Acceptance criteria: Obstacle Library | Business Analyst task for 'Obstacle Library'. Deliverable sized to 3 SP. | 2025-11-18 | 2025-11-19 | To Do | Low | 3
23 | Data_Liam | Data Team | ETL pipeline: Pet Companions | Data Team task for 'Pet Companions'. Deliverable sized to 3 SP. | 2025-11-14 | 2025-11-16 | To Do | Medium | 3
23 | Data_Liam | Data Team | ETL pipeline: Analytics & Telemetry | Data Team task for 'Analytics & Telemetry'. Deliverable sized to 5 SP. | 2025-11-18 | 2025-11-19 | To Do | Medium | 5
23 | FE_Emily | Frontend | UX polish: Leaderboard | Frontend task for 'Leaderboard'. Deliverable sized to 8 SP. | 2025-11-11 | 2025-11-15 | To Do | Medium | 8
23 | FE_David | Frontend | Responsive layout: Accessibility | Frontend task for 'Accessibility'. Deliverable sized to 5 SP. | 2025-11-10 | 2025-11-13 | To Do | Medium | 5
23 | FE_Noah | Frontend | Implement UI: Daily Challenges | Frontend task for 'Daily Challenges'. Deliverable sized to 3 SP. | 2025-11-11 | 2025-11-13 | To Do | Low | 3
23 | FE_Noah | Frontend | Animations & VFX: Anti-cheat | Frontend task for 'Anti-cheat'. Deliverable sized to 5 SP. | 2025-11-11 | 2025-11-14 | To Do | Medium | 5
23 | FE_David | Frontend | Animations & VFX: Guilds & Chat | Frontend task for 'Guilds & Chat'. Deliverable sized to 3 SP. | 2025-11-13 | 2025-11-15 | To Do | Medium | 3
23 | QA_Daniel | QA | Regression suite update: Obstacle Library | QA task for 'Obstacle Library'. Deliverable sized to 3 SP. | 2025-11-12 | 2025-11-13 | To Do | Medium | 3
23 | QA_Olivia | QA | Test plan: A/B Testing Framework | QA task for 'A/B Testing Framework'. Deliverable sized to 5 SP. | 2025-11-18 | 2025-11-21 | To Do | High | 5
23 | QA_Olivia | QA | Regression suite update: Analytics & Telemetry | QA task for 'Analytics & Telemetry'. Deliverable sized to 5 SP. | 2025-11-16 | 2025-11-19 | To Do | Low | 5
23 | QA_Daniel | QA | Test data setup: Level Generator | QA task for 'Level Generator'. Deliverable sized to 5 SP. | 2025-11-12 | 2025-11-15 | To Do | High | 5
24 | BE_Ava | Backend | Performance tuning: Analytics & Telemetry | Backend task for 'Analytics & Telemetry'. Deliverable sized to 5 SP. | 2025-11-25 | 2025-11-26 | To Do | High | 5
24 | BE_Michael | Backend | Leaderboard/Guild service: A/B Testing Framework | Backend task for 'A/B Testing Framework'. Deliverable sized to 3 SP. | 2025-12-02 | 2025-12-03 | To Do | High | 3
24 | BE_Sophia | Backend | Game logic service: Season Pass | Backend task for 'Season Pass'. Deliverable sized to 8 SP. | 2025-11-28 | 2025-12-01 | To Do | Medium | 8
24 | BE_Ava | Backend | Authentication/Session: Live Ops Tooling | Backend task for 'Live Ops Tooling'. Deliverable sized to 5 SP. | 2025-11-26 | 2025-11-29 | To Do | Medium | 5
24 | BE_Michael | Backend | Leaderboard/Guild service: Cloud Save | Backend task for 'Cloud Save'. Deliverable sized to 5 SP. | 2025-11-30 | 2025-12-03 | To Do | Medium | 5
24 | BA_John | Business Analyst | Stakeholder workshop: Daily Challenges | Business Analyst task for 'Daily Challenges'. Deliverable sized to 5 SP. | 2025-11-27 | 2025-11-29 | To Do | Low | 5
24 | BA_Alice | Business Analyst | Stakeholder workshop: Pet Companions | Business Analyst task for 'Pet Companions'. Deliverable sized to 8 SP. | 2025-11-28 | 2025-12-03 | To Do | Medium | 8
24 | BA_John | Business Analyst | Epic scoping: Season Pass | Business Analyst task for 'Season Pass'. Deliverable sized to 3 SP. | 2025-11-30 | 2025-12-02 | To Do | High | 3
24 | Data_Liam | Data Team | Balance analysis: Offline Mode | Data Team task for 'Offline Mode'. Deliverable sized to 5 SP. | 2025-11-29 | 2025-12-01 | To Do | Low | 5
24 | Data_Liam | Data Team | Dashboard build: Power-ups & Boosts | Data Team task for 'Power-ups & Boosts'. Deliverable sized to 5 SP. | 2025-11-27 | 2025-11-30 | To Do | Medium | 5
24 | FE_David | Frontend | UX polish: Analytics & Telemetry | Frontend task for 'Analytics & Telemetry'. Deliverable sized to 8 SP. | 2025-11-24 | 2025-11-29 | To Do | High | 8
24 | FE_Emily | Frontend | UX polish: Anti-cheat | Frontend task for 'Anti-cheat'. Deliverable sized to 5 SP. | 2025-11-29 | 2025-12-01 | To Do | Medium | 5
24 | FE_Noah | Frontend | Responsive layout: Beta Release | Frontend task for 'Beta Release'. Deliverable sized to 8 SP. | 2025-11-25 | 2025-11-30 | To Do | Medium | 8
24 | FE_Emily | Frontend | Animations & VFX: Beta Release | Frontend task for 'Beta Release'. Deliverable sized to 3 SP. | 2025-11-29 | 2025-11-30 | To Do | High | 3
24 | QA_Daniel | QA | Regression suite update: Guilds & Chat | QA task for 'Guilds & Chat'. Deliverable sized to 5 SP. | 2025-11-30 | 2025-12-03 | To Do | High | 5
24 | QA_Olivia | QA | Functional test: Shop & IAP | QA task for 'Shop & IAP'. Deliverable sized to 8 SP. | 2025-11-30 | 2025-12-04 | To Do | Medium | 8
24 | QA_Daniel | QA | Regression suite update: Character Customization | QA task for 'Character Customization'. Deliverable sized to 5 SP. | 2025-11-29 | 2025-12-02 | To Do | High | 5
25 | BE_Sophia | Backend | Game logic service: Power-ups & Boosts | Backend task for 'Power-ups & Boosts'. Deliverable sized to 5 SP. | 2025-12-12 | 2025-12-13 | To Do | Low | 5
25 | BE_Ava | Backend | Leaderboard/Guild service: Shop & IAP | Backend task for 'Shop & IAP'. Deliverable sized to 5 SP. | 2025-12-08 | 2025-12-10 | To Do | High | 5
25 | BE_Ava | Backend | Game logic service: Push Notifications | Backend task for 'Push Notifications'. Deliverable sized to 3 SP. | 2025-12-11 | 2025-12-13 | To Do | High | 3
25 | BE_Michael | Backend | Leaderboard/Guild service: Pet Companions | Backend task for 'Pet Companions'. Deliverable sized to 3 SP. | 2025-12-18 | 2025-12-19 | To Do | Medium | 3
25 | BE_Michael | Backend | Performance tuning: Leaderboard | Backend task for 'Leaderboard'. Deliverable sized to 5 SP. | 2025-12-10 | 2025-12-13 | To Do | Medium | 5
25 | BE_Sophia | Backend | Performance tuning: Season Pass | Backend task for 'Season Pass'. Deliverable sized to 5 SP. | 2025-12-09 | 2025-12-12 | To Do | Low | 5
25 | BA_Alice | Business Analyst | Backlog refinement: Live Ops Tooling | Business Analyst task for 'Live Ops Tooling'. Deliverable sized to 5 SP. | 2025-12-16 | 2025-12-17 | To Do | Medium | 5
25 | BA_Alice | Business Analyst | Stakeholder workshop: Daily Challenges | Business Analyst task for 'Daily Challenges'. Deliverable sized to 5 SP. | 2025-12-13 | 2025-12-15 | To Do | Medium | 5
25 | BA_John | Business Analyst | Acceptance criteria: Power-ups & Boosts | Business Analyst task for 'Power-ups & Boosts'. Deliverable sized to 8 SP. | 2025-12-14 | 2025-12-16 | To Do | Low | 8
25 | Data_Liam | Data Team | ETL pipeline: Push Notifications | Data Team task for 'Push Notifications'. Deliverable sized to 3 SP. | 2025-12-09 | 2025-12-10 | To Do | High | 3
25 | Data_Liam | Data Team | Balance analysis: Live Ops Tooling | Data Team task for 'Live Ops Tooling'. Deliverable sized to 5 SP. | 2025-12-14 | 2025-12-17 | To Do | High | 5
25 | FE_Emily | Frontend | Animations & VFX: Daily Challenges | Frontend task for 'Daily Challenges'. Deliverable sized to 3 SP. | 2025-12-18 | 2025-12-19 | To Do | Low | 3
25 | FE_Noah | Frontend | Responsive layout: Offline Mode | Frontend task for 'Offline Mode'. Deliverable sized to 5 SP. | 2025-12-14 | 2025-12-17 | To Do | Medium | 5
25 | FE_David | Frontend | Implement UI: Accessibility | Frontend task for 'Accessibility'. Deliverable sized to 5 SP. | 2025-12-09 | 2025-12-12 | To Do | Low | 5
25 | FE_Emily | Frontend | Animations & VFX: Live Ops Tooling | Frontend task for 'Live Ops Tooling'. Deliverable sized to 3 SP. | 2025-12-14 | 2025-12-15 | To Do | Medium | 3
25 | FE_Noah | Frontend | Responsive layout: Power-ups & Boosts | Frontend task for 'Power-ups & Boosts'. Deliverable sized to 3 SP. | 2025-12-13 | 2025-12-15 | To Do | Medium | 3
25 | FE_Emily | Frontend | Animations & VFX: Level Generator | Frontend task for 'Level Generator'. Deliverable sized to 3 SP. | 2025-12-17 | 2025-12-19 | To Do | Medium | 3
25 | FE_David | Frontend | UX polish: Shop & IAP | Frontend task for 'Shop & IAP'. Deliverable sized to 3 SP. | 2025-12-15 | 2025-12-16 | To Do | Medium | 3
25 | QA_Olivia | QA | Test data setup: Pet Companions | QA task for 'Pet Companions'. Deliverable sized to 3 SP. | 2025-12-10 | 2025-12-12 | To Do | Medium | 3
25 | QA_Daniel | QA | Exploratory testing: Guilds & Chat | QA task for 'Guilds & Chat'. Deliverable sized to 3 SP. | 2025-12-13 | 2025-12-14 | To Do | Medium | 3
25 | QA_Daniel | QA | Regression suite update: Character Customization | QA task for 'Character Customization'. Deliverable sized to 3 SP. | 2025-12-12 | 2025-12-14 | To Do | Medium | 3
25 | QA_Daniel | QA | Test data setup: Level Generator | QA task for 'Level Generator'. Deliverable sized to 3 SP. | 2025-12-15 | 2025-12-17 | To Do | Medium | 3
25 | QA_Olivia | QA | Test plan: Shop & IAP | QA task for 'Shop & IAP'. Deliverable sized to 5 SP. | 2025-12-10 | 2025-12-13 | To Do | Low | 5
26 | BE_Ava | Backend | Game logic service: Leaderboard | Backend task for 'Leaderboard'. Deliverable sized to 5 SP. | 2025-12-29 | 2025-12-31 | To Do | Medium | 5
26 | BE_Sophia | Backend | Leaderboard/Guild service: Leaderboard | Backend task for 'Leaderboard'. Deliverable sized to 8 SP. | 2025-12-29 | 2025-12-31 | To Do | Medium | 8
26 | BE_Michael | Backend | Authentication/Session: Social Sharing | Backend task for 'Social Sharing'. Deliverable sized to 5 SP. | 2025-12-27 | 2025-12-29 | To Do | High | 5
26 | BE_Michael | Backend | Performance tuning: Shop & IAP | Backend task for 'Shop & IAP'. Deliverable sized to 3 SP. | 2025-12-22 | 2025-12-23 | To Do | Medium | 3
26 | BE_Ava | Backend | API endpoint: Inventory | Backend task for 'Inventory'. Deliverable sized to 5 SP. | 2025-12-30 | 2026-01-01 | To Do | Low | 5
26 | BA_John | Business Analyst | Acceptance criteria: Power-ups & Boosts | Business Analyst task for 'Power-ups & Boosts'. Deliverable sized to 5 SP. | 2025-12-30 | 2026-01-01 | To Do | Medium | 5
26 | BA_Alice | Business Analyst | Acceptance criteria: Core Runner Mechanics | Business Analyst task for 'Core Runner Mechanics'. Deliverable sized to 8 SP. | 2025-12-25 | 2025-12-29 | To Do | Low | 8
26 | BA_John | Business Analyst | Stakeholder workshop: Accessibility | Business Analyst task for 'Accessibility'. Deliverable sized to 5 SP. | 2025-12-30 | 2026-01-02 | To Do | Low | 5
26 | Data_Liam | Data Team | A/B experiment design: Analytics & Telemetry | Data Team task for 'Analytics & Telemetry'. Deliverable sized to 8 SP. | 2025-12-24 | 2025-12-29 | To Do | High | 8
26 | FE_Emily | Frontend | Implement UI: Beta Release | Frontend task for 'Beta Release'. Deliverable sized to 5 SP. | 2025-12-27 | 2025-12-30 | To Do | Medium | 5
26 | FE_David | Frontend | UX polish: Weekly Boss Chase | Frontend task for 'Weekly Boss Chase'. Deliverable sized to 5 SP. | 2025-12-24 | 2025-12-25 | To Do | Low | 5
26 | FE_Noah | Frontend | Animations & VFX: Daily Challenges | Frontend task for 'Daily Challenges'. Deliverable sized to 8 SP. | 2025-12-29 | 2026-01-01 | To Do | Medium | 8
26 | FE_Emily | Frontend | UX polish: Analytics & Telemetry | Frontend task for 'Analytics & Telemetry'. Deliverable sized to 5 SP. | 2025-12-27 | 2025-12-30 | To Do | Medium | 5
26 | FE_David | Frontend | Implement UI: Social Sharing | Frontend task for 'Social Sharing'. Deliverable sized to 5 SP. | 2025-12-24 | 2025-12-26 | To Do | High | 5
26 | QA_Olivia | QA | Regression suite update: Anti-cheat | QA task for 'Anti-cheat'. Deliverable sized to 5 SP. | 2025-12-28 | 2025-12-29 | To Do | Medium | 5
26 | QA_Daniel | QA | Test data setup: Guilds & Chat | QA task for 'Guilds & Chat'. Deliverable sized to 5 SP. | 2025-12-25 | 2025-12-27 | To Do | Low | 5
26 | QA_Olivia | QA | Test plan: Guilds & Chat | QA task for 'Guilds & Chat'. Deliverable sized to 5 SP. | 2025-12-25 | 2025-12-26 | To Do | High | 5
26 | QA_Daniel | QA | Functional test: Launch & Post-Launch | QA task for 'Launch & Post-Launch'. Deliverable sized to 5 SP. | 2025-12-26 | 2025-12-27 | To Do | Medium | 5

## Overview
Item | Value
Game Theme | Skyward Sprinters
Game Concept | Players race along floating islands, dodging obstacles and collecting 'Wind Shards'. Core loops: daily runs, weekly boss chases, seasonal events, and guild leaderboards. Monetization via cosmetics and season pass; progression via upgrades and pet companions.
Timeline | Jan 6, 2025 – Dec 2025
Sprint Length (days) | 14
Number of Sprints | 26
Total Tasks (generated) | 505
Avg Tasks per Sprint | 19.42

## Team_Stats
Team | Task Count
Backend | 136
Business Analyst | 95
Data Team | 46
Frontend | 138
QA | 90

## Member_SP_Totals
Assignee | Total Story Points (All Sprints)
BA_Alice | 220
BA_John | 227
BE_Ava | 221
BE_Michael | 228
BE_Sophia | 223
Data_Liam | 219
FE_David | 219
FE_Emily | 223
FE_Noah | 210
QA_Daniel | 220
QA_Olivia | 218